## Summary
Folio3 Project Estimation
Maintenance Request
Summary of Estimates
Client Name | The ignite studio
Project Manager | Ahsan Raza
Date | 2026-10-10
Version | 1
Efforts (in hours)
Task Summary | Minimum | Maximum | Comments | Avg | Resources | Weeks
Backend Development Estimates | 27.26 | 49.73 | Grand total of the Backend sheet | 38.49 | 1 | 0.96
Mobile Development Estimates | 0 | 0 | Grand total of the Mobile sheet | 0 | 1 | 0
Admin Development Estimates | 35.26 | 59.28 | Grand total of the Web / Admin sheet | 47.27 | 1 | 1.18
QA Estimates | 13 | 24.2 | Grand total of the QA sheet | 18.6 | 1 | 0.47
GD Estimates | 0 | 0 | Other Estimates sheet | 0 | 1 | 0
PM Estimates | 4 | 8 | Other Estimates sheet | 6 | 1 | 0.15
PDM Estimates | 0 | 0 | Other Estimates sheet | 0 | 1 | 0
Cross-cutting Estimates | 0 | 0 | Other Estimates sheet: deployment, documentation and the like | 0 | 1 | 0
Design Estimates | 0 | 0 | Counted in the total only when Design is switched on below | 0 | 1 | 0
Total | 79.52 | 141.21 |  | 110.37
List of Special Considerations, where applicable:
Tasks | Action |  | Comments
Application type (mobile, desktop, web) | Backend + Web |  | From the tracks that have work
Platforms/OS supported | Not specified |  | Confirm with the client
Browsers supported | No specific browser support target beyond browsers compatible with the chosen implementation. |  | Clarify answer Q-2
Deployment (cloud, dedicated server, enterprise internal network) | Not specified |  | Confirm with the client
Performance, Load requirements | Not specified |  | Confirm with the client
Security requirements | Not specified |  | Confirm with the client
Documentation requirements | Not specified |  | Confirm with the client
Other custom? | No
Parameters
Include Design in total | Yes
Hours per week | 40
Feedback rounds | 2
Stack chosen by | undecided
Delivery model | Solely agentic
How to read the hours
Each task's Minimum and Maximum are the hours it takes to deliver. Most of the work is done by AI agents; a person's hours are added only where a person is needed (client acceptance, design sign-off, project liaison, accounts and keys).
Elapsed time
Planning (minutes) | 15
Build critical path (days) | 3.71 | 6.51
Assumptions
Spec question Q-6: Should the 1280 px table-layout target be configurable, or remain the fixed target specified for this release? → Keep 1280 px as the fixed table-layout target. (answered)
Spec question Q-7: Should the request detail screen add states for loading a request and for failures other than not-found? → Keep the specified detail behavior: show the request on success and “Request not found.” for an unknown ID; add no other fetch states. (answered)
Spec question Q-8: How should AC-1.1 verify that a newly created request can be retrieved? → Compare the create response with a separate get-by-ID API response. (answered)
No design was drawn for this estimate (it was left out at the start): the UI tasks are sized from the requirements alone, with no approved screens behind them, so their range is wider. A build from this estimate draws the design and has it approved before its plan.
Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
Split before the build: EST-4, EST-5, EST-6 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).

## Dev Backend Estimates
Development Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
| Grand Total (in hours) | 27.26 | 49.73 | Sum of development, other activities and research efforts.
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | Request data and HTTP API | 27.26 | 49.73
| Request data model, migrations, persistence, and seed data | 2.88 | 5.76 | Request record fields: ID, title, area, priority, optional description, status, and UTC creation time; Database migrations for the request record; Persistence across application restarts; On empty-database initialization, seed exactly eight requests: four Open including exactly one Urgent, two In progress, two Done, with every supported area represented | Factory | REQ-1, REQ-2, REQ-3, REQ-6 | EST-1
| List requests API | 3.24 | 6.48 | List requests operation with optional single-status filter; Return all requests or only those matching the requested status, ordered newest first; Return the seeded request list and status counts after initialization | Factory | REQ-2, REQ-4, REQ-5 | EST-2
| Get request by ID API | 1.94 | 3.89 | Get-by-ID operation returns the persisted request record; Unknown ID returns a not-found response; Create response and separate get-by-ID response contain the same ID and request-field values | Factory | REQ-1, REQ-3, REQ-4, REQ-20 | EST-3
| Create request operation and validation rules | 9.6 | 16.8 | Create request operation assigns a system-generated ID, UTC creation time, and Open status; Trim surrounding title whitespace before validating and storing; require 3 to 80 characters; Require area Kitchen, Meeting room, Open desk, Washroom, or Reception; Require priority Low, Normal, or Urgent; Allow an optional description of at most 500 characters; Invalid values return an error naming the invalid field; Keep title, area, priority, and description fixed after creation; reject attempts to change those fields or delete a request; Expose only the specified request operations; do not provide additional request operations | Factory | REQ-4, REQ-6, REQ-7, REQ-8 | EST-4
| Request status-change operation and transition rules | 9.6 | 16.8 | Accept Open to In progress, In progress to Done, and Done to Open only; Reject all other status changes without changing the record; Unknown request ID returns not found; Missing status-change body and unrecognized status value return errors without changing the record; Do not expose edit or delete operations | Factory | REQ-4, REQ-8, REQ-9 | EST-5
| Development Total Efforts (in hours) | 27.26 | 49.73
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | None | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | None | 0 | 0 | No research task in this estimate
| Research Total Efforts (in hours) | 0 | 0
S.No | Assumptions & Constraints
1 | Spec question Q-6: Should the 1280 px table-layout target be configurable, or remain the fixed target specified for this release? → Keep 1280 px as the fixed table-layout target. (answered)
2 | Spec question Q-7: Should the request detail screen add states for loading a request and for failures other than not-found? → Keep the specified detail behavior: show the request on success and “Request not found.” for an unknown ID; add no other fetch states. (answered)
3 | Spec question Q-8: How should AC-1.1 verify that a newly created request can be retrieved? → Compare the create response with a separate get-by-ID API response. (answered)
4 | No design was drawn for this estimate (it was left out at the start): the UI tasks are sized from the requirements alone, with no approved screens behind them, so their range is wider. A build from this estimate draws the design and has it approved before its plan.
5 | Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
6 | Split before the build: EST-4, EST-5, EST-6 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).
S.No | Risks
1 | Estimates will increase in case of change in requirement

## Dev Mobile Estimates
Development Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
Not in scope: no work in this estimate
| Grand Total (in hours) | 0 | 0 | Sum of development, other activities and research efforts.
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
| None | 0 | 0
| Development Total Efforts (in hours) | 0 | 0
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | None | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | None | 0 | 0 | No research task in this estimate
| Research Total Efforts (in hours) | 0 | 0

## Dev Web Estimates
Development Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
| Grand Total (in hours) | 35.26 | 59.28 | Sum of development, other activities and research efforts.
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | Requests list and request creation | 14.98 | 24.96
| Requests list screen | 9.36 | 15.6 | Hive Works wordmark and signed-in demo-user initials SC; Status filter choices All, Open, In progress, and Done; All selected initially; Newest-first request list, with stacked cards at 375 px and table rows at 1280 px; no horizontal page scroll at those widths; New request button; Loading state “Loading requests…”; empty state “No requests here.”; load-error state “Could not load requests.” with Retry button; Selecting a filter loads its list; returning from detail retains the selected filter and refreshes the list; After successful creation, show the new Open request at the top and select All; Created date displayed without time or timezone, in a date-only format such as “8 Oct 2026”; Status and priority badges use the specified colors and include readable text labels; Every control is keyboard reachable; text meets WCAG AA contrast | Factory | REQ-10, REQ-11, REQ-13, REQ-16, REQ-21, REQ-22, REQ-23 | EST-7
| New request dialog | 5.62 | 9.36 | Dialog with labeled Title, Area, Priority, and Description fields; Priority defaults to Normal; Create and Cancel controls; Show a field's validation error under that field and keep the dialog open; include the Title error “Title must be 3 to 80 characters.” for a two-character title; On non-validation create failure, show “Could not create request.”, retain entered values, and allow retry through Create; On successful creation, close the dialog and show the new Open request through the Requests list's All filter; Every field is labeled and every control is keyboard reachable | Factory | REQ-7, REQ-12, REQ-13, REQ-14, REQ-15, REQ-22 | EST-8
2 | Request detail and status changes | 7.8 | 12.48
| Request detail screen | 7.8 | 12.48 | Back link; request title, area, priority badge, status badge, created date, and description or “No description.”; Show “Request not found.” and a link back to Requests for an unknown ID; Show Start work for Open, Mark done for In progress, and Reopen for Done; After a successful status change, show the new status badge and corresponding next action; on failure show “Could not update the request.” and retain the prior status badge; Status and priority badges use the specified colors and include readable text labels; Created date displayed without time or timezone, in a date-only format such as “8 Oct 2026”; Every control is keyboard reachable; text meets WCAG AA contrast | Factory | REQ-11, REQ-17, REQ-18, REQ-19, REQ-20, REQ-21, REQ-22, REQ-23 | EST-9
3 | Visual presentation and accessibility | 12.48 | 21.84
| Web application shell and light theme | 12.48 | 21.84 | Browser-accessible web application shell and page layout; One light theme with sans-serif text, neutral background, and near-black text | Factory | REQ-1, REQ-21 | EST-6
| Development Total Efforts (in hours) | 35.26 | 59.28
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | None | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | None | 0 | 0 | No research task in this estimate
| Research Total Efforts (in hours) | 0 | 0
S.No | Assumptions & Constraints
1 | Spec question Q-6: Should the 1280 px table-layout target be configurable, or remain the fixed target specified for this release? → Keep 1280 px as the fixed table-layout target. (answered)
2 | Spec question Q-7: Should the request detail screen add states for loading a request and for failures other than not-found? → Keep the specified detail behavior: show the request on success and “Request not found.” for an unknown ID; add no other fetch states. (answered)
3 | Spec question Q-8: How should AC-1.1 verify that a newly created request can be retrieved? → Compare the create response with a separate get-by-ID API response. (answered)
4 | No design was drawn for this estimate (it was left out at the start): the UI tasks are sized from the requirements alone, with no approved screens behind them, so their range is wider. A build from this estimate draws the design and has it approved before its plan.
5 | Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
6 | Split before the build: EST-4, EST-5, EST-6 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).
S.No | Risks
1 | Estimates will increase in case of change in requirement

## QA Estimates
QA Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
| Grand Total Efforts (in hours) | 13 | 24.2 | Sum of QA and Misc.
S.No | Estimation Summary | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | Test Plan/Strategy | 0 | 0 | Test planning, with the test plan, strategy and traceability matrix as outputs. Not sized in this estimate
2 | Set up of Test Environments | 0 | 0 | Setting up code and white box test environments. Not sized in this estimate
3 | Validation and Smoke test cases | 3.6 | 7.2 | Test cases to execute while debugging and white box testing
| Automated request business-rule test cases | 3.6 | 7.2 | Automated cases for valid creation with Open status; missing and too-short title rejection; missing area rejection; too-long description rejection; Automated cases for all three allowed status transitions and rejection of a disallowed transition; Automated cases for filtered newest-first listing and unknown-ID not-found behavior | Factory | REQ-24 | EST-10
4 | Validation testing | 5.4 | 9 | Testing cycles; the detail is below
| Testing Cycle 1 | 5.4 | 9
5 | Smoke testing | 0 | 0 | Smoke testing after each deployment, including preparation. Not sized in this estimate
6 | Multi Browser Compatibility testing | 0 | 0 | Browser, OS and device compatibility. Not sized in this estimate
7 | UAT | 4 | 8 | Client user acceptance testing support
| Client acceptance testing | 4 | 8 | Client UAT is a required human acceptance activity and does not deliver a specification requirement. | Human |  | EST-12
8 | Misc. Optional testing | 0 | 0 | Other testing named in the breakdown, and supervisor gate time. Not sized in this estimate
| Total QA Efforts | 13 | 24.2 | Total hours of QA
S.No | Validation Testing | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
Testing Cycle 1
1 | Automated list-to-completion end-to-end test | 5.4 | 9 | Run the list, create, open, Start work, Mark done, and Done-filter workflow; Verify the created request appears at the top, then appears in the Done-filtered list after completion | Factory | REQ-24 | EST-11
| Total Testing Cycle 1 | 5.4 | 9 | Sum of testing cycle 1
S.No | Assumptions & Constraints
1 | Spec question Q-6: Should the 1280 px table-layout target be configurable, or remain the fixed target specified for this release? → Keep 1280 px as the fixed table-layout target. (answered)
2 | Spec question Q-7: Should the request detail screen add states for loading a request and for failures other than not-found? → Keep the specified detail behavior: show the request on success and “Request not found.” for an unknown ID; add no other fetch states. (answered)
3 | Spec question Q-8: How should AC-1.1 verify that a newly created request can be retrieved? → Compare the create response with a separate get-by-ID API response. (answered)
4 | No design was drawn for this estimate (it was left out at the start): the UI tasks are sized from the requirements alone, with no approved screens behind them, so their range is wider. A build from this estimate draws the design and has it approved before its plan.
5 | Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
6 | Split before the build: EST-4, EST-5, EST-6 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).
S.No | Risks
1 | Estimates will increase in case of change in requirement

## Design Estimates
Design Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
Not in scope: no work in this estimate
| Grand Total (in hours) | 0 | 0 | Sum of development, other activities and research efforts.
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
| None | 0 | 0
| Development Total Efforts (in hours) | 0 | 0
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | None | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | None | 0 | 0 | No research task in this estimate
| Research Total Efforts (in hours) | 0 | 0

## Other Estimates
Other Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
GD
Not in scope: no work in this estimate
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | None | 0 | 0
| GD TOTAL | 0 | 0
PM
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | Client liaison and project management | 4 | 8 | Required human client liaison and project-management overhead; factory planning and coordination of its own work are excluded. | Human |  | EST-13
| PM TOTAL | 4 | 8
PDM
Not in scope: no work in this estimate
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | None | 0 | 0
| PDM TOTAL | 0 | 0
Cross-cutting
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id
1 | None | 0 | 0
| Cross-cutting TOTAL | 0 | 0

## All Tasks
All tasks: Maintenance Request
Filter or sort any column. The Total row adds up only the rows the filter shows.
Task id | Task | Track | Module | Executor | Requirement id(s) | Minimum | Maximum
EST-1 | Request data model, migrations, persistence, and seed data | Backend | Request data and HTTP API | Factory | REQ-1, REQ-2, REQ-3, REQ-6 | 2.88 | 5.76
EST-2 | List requests API | Backend | Request data and HTTP API | Factory | REQ-2, REQ-4, REQ-5 | 3.24 | 6.48
EST-3 | Get request by ID API | Backend | Request data and HTTP API | Factory | REQ-1, REQ-3, REQ-4, REQ-20 | 1.94 | 3.89
EST-4 | Create request operation and validation rules | Backend | Request data and HTTP API | Factory | REQ-4, REQ-6, REQ-7, REQ-8 | 9.6 | 16.8
EST-5 | Request status-change operation and transition rules | Backend | Request data and HTTP API | Factory | REQ-4, REQ-8, REQ-9 | 9.6 | 16.8
EST-6 | Web application shell and light theme | Web | Visual presentation and accessibility | Factory | REQ-1, REQ-21 | 12.48 | 21.84
EST-7 | Requests list screen | Web | Requests list and request creation | Factory | REQ-10, REQ-11, REQ-13, REQ-16, REQ-21, REQ-22, REQ-23 | 9.36 | 15.6
EST-8 | New request dialog | Web | Requests list and request creation | Factory | REQ-7, REQ-12, REQ-13, REQ-14, REQ-15, REQ-22 | 5.62 | 9.36
EST-9 | Request detail screen | Web | Request detail and status changes | Factory | REQ-11, REQ-17, REQ-18, REQ-19, REQ-20, REQ-21, REQ-22, REQ-23 | 7.8 | 12.48
EST-10 | Automated request business-rule test cases | QA | Automated verification | Factory | REQ-24 | 3.6 | 7.2
EST-11 | Automated list-to-completion end-to-end test | QA | Automated verification | Factory | REQ-24 | 5.4 | 9
EST-12 | Client acceptance testing | QA | Automated verification | Human |  | 4 | 8
EST-13 | Client liaison and project management | PM | Automated verification | Human |  | 4 | 8
| Total (rows shown) |  |  |  |  | 79.52 | 141.21