## Summary
Folio3 Project Estimation
Maintenance Request
Summary of Estimates
Client Name | The ignite studio
Project Manager | Ahsan Raza
Date | 2026-10-10
Version | 1
| Efforts (in hours) |  |  | API credits (USD)
Task Summary | Minimum | Maximum | Comments | API min ($) | API max ($) | Avg | Resources | Weeks
Backend Development Estimates | 27.26 | 49.73 | Grand total of the Backend sheet | 4.58 | 21.95 | 38.49 | 1 | 0.96
Mobile Development Estimates | 0 | 0 | Grand total of the Mobile sheet | 0 | 0 | 0 | 1 | 0
Admin Development Estimates | 35.26 | 59.28 | Grand total of the Web / Admin sheet | 5.61 | 26.94 | 47.27 | 1 | 1.18
QA Estimates | 13 | 24.2 | Grand total of the QA sheet | 1.49 | 7.18 | 18.6 | 1 | 0.47
GD Estimates | 0 | 0 | Other Estimates sheet | 0 | 0 | 0 | 1 | 0
PM Estimates | 4 | 8 | Other Estimates sheet | 0 | 0 | 6 | 1 | 0.15
PDM Estimates | 0 | 0 | Other Estimates sheet | 0 | 0 | 0 | 1 | 0
Cross-cutting Estimates | 0 | 0 | Other Estimates sheet: deployment, documentation and the like | 0 | 0 | 0 | 1 | 0
Design Estimates | 0 | 0 | Counted in the total only when Design is switched on below | 0 | 0 | 0 | 1 | 0
Total | 79.52 | 141.21 |  | 12.66 | 64.09 | 110.37
Project-level API (planning, design, breakdown and estimate, once per project) |  |  |  | 0.98 | 8.02
List of Special Considerations, where applicable:
Tasks | Action |  | Comments
Application type (mobile, desktop, web) | Backend + Web |  | From the tracks that have work
Platforms/OS supported | Not specified |  | Confirm with the client
Browsers supported | No specific browser support target beyond browsers compatible with the chosen implementation. |  | Clarify answer Q-2
Deployment (cloud, dedicated server, enterprise internal network) | Not specified |  | Confirm with the client
Performance, Load requirements | Not specified |  | Confirm with the client
Security requirements | Not specified |  | Confirm with the client
Documentation requirements | Not specified |  | Confirm with the client
Other custom? | No
Parameters
Include Design in total | Yes
Hours per week | 40
Feedback rounds | 2
Stack chosen by | undecided
Delivery model | Solely agentic
Size band | M
API credit cost (USD)
Phase | Min ($) | Max ($) | Based on
planning | 0.51 | 7.07 | measured: p10-p90 of 8 runs (8 ledger)
breakdown-estimate | 0.47 | 0.95 | measured: p10-p90 of 3 runs (3 ledger)
build | 11.62 | 54.33 | measured: p10-p90 of 6 runs (3 ledger, 3 eval)
verification | 0.06 | 1.74 | measured: p10-p90 of 4 runs (2 ledger, 2 eval)
API credit cost total | 12.66 | 64.09
Confidence | partial (21 measured records)
Per task | API min and max ($) on each task sheet: the task's share of build and verification, by its hours. A human task costs nothing; planning, design, breakdown and estimate are spent once per run.
How to read the hours
Each task's Minimum and Maximum are the hours it takes to deliver. Most of the work is done by AI agents; a person's hours are added only where a person is needed (client acceptance, design sign-off, project liaison, accounts and keys). The API credits beside the hours are what the AI spends to build and verify each task.
Executor | Factory: the factory's hours only. Joint: the factory with a person's steps (keys, accounts, go-live). Human: a person's hours only (UAT, design sign-off, PM).
Factory hours basis | cold-start: each task's sized hours, a reference size, until this factory has built enough tasks of its class (3 or more)
Hours by executor | Minimum | Maximum
Factory | 71.52 | 125.21
Human | 8 | 16
Elapsed time
Planning (minutes) | 15
Build critical path (days) | 3.71 | 6.51
Assumptions
Spec question Q-6: Should the 1280 px table-layout target be configurable, or remain the fixed target specified for this release? → Keep 1280 px as the fixed table-layout target. (answered)
Spec question Q-7: Should the request detail screen add states for loading a request and for failures other than not-found? → Keep the specified detail behavior: show the request on success and “Request not found.” for an unknown ID; add no other fetch states. (answered)
Spec question Q-8: How should AC-1.1 verify that a newly created request can be retrieved? → Compare the create response with a separate get-by-ID API response. (answered)
No design was drawn for this estimate (it was left out at the start): the UI tasks are sized from the requirements alone, with no approved screens behind them, so their range is wider. A build from this estimate draws the design and has it approved before its plan.
Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
Split before the build: EST-4, EST-5, EST-6 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).

## Dev Backend Estimates
Development Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
| Grand Total (in hours) | 27.26 | 49.73 | Sum of development, other activities and research efforts. |  |  | API total ($) | 4.58 | 21.95
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | Request data and HTTP API | 27.26 | 49.73 |  |  |  |  | 4.58 | 21.95
| Request data model, migrations, persistence, and seed data | 2.88 | 5.76 | Request record fields: ID, title, area, priority, optional description, status, and UTC creation time; Database migrations for the request record; Persistence across application restarts; On empty-database initialization, seed exactly eight requests: four Open including exactly one Urgent, two In progress, two Done, with every supported area represented (1 entity (Request) with migration, persistence and seed data; seed rows do not add entities: small. [be-data backend 4-8 h, small x0.6]) | Factory | REQ-1, REQ-2, REQ-3, REQ-6 | EST-1 | 0.51 | 2.46
| List requests API | 3.24 | 6.48 | List requests operation with optional single-status filter; Return all requests or only those matching the requested status, ordered newest first; Return the seeded request list and status counts after initialization (One optional status filter plus newest-first ordering and status counts: typical. The filter makes this larger than the closest approved small endpoint, which had no filter. [be-endpoint backend 3-6 h, verify easy x0.9]) | Factory | REQ-2, REQ-4, REQ-5 | EST-2 | 0.58 | 2.77
| Get request by ID API | 1.94 | 3.89 | Get-by-ID operation returns the persisted request record; Unknown ID returns a not-found response; Create response and separate get-by-ID response contain the same ID and request-field values (Plain get-by-ID read with a not-found case; no filters or joins: small, matching the approved small task. [be-endpoint backend 3-6 h, small x0.6, verify easy x0.9]) | Factory | REQ-1, REQ-3, REQ-4, REQ-20 | EST-3 | 0.35 | 1.66
| Create request operation and validation rules | 9.6 | 16.8 | Create request operation assigns a system-generated ID, UTC creation time, and Open status; Trim surrounding title whitespace before validating and storing; require 3 to 80 characters; Require area Kitchen, Meeting room, Open desk, Washroom, or Reception; Require priority Low, Normal, or Urgent; Allow an optional description of at most 500 characters; Invalid values return an error naming the invalid field; Keep title, area, priority, and description fixed after creation; reject attempts to change those fields or delete a request; Expose only the specified request operations; do not provide additional request operations (11 distinct rules: 3 creation assignments, 4 field validations, field-specific errors, fixed fields, no deletion, and an operation allowlist: large, matching the approved large task. [be-rules backend 8-14 h, large x1.6]) | Factory | REQ-4, REQ-6, REQ-7, REQ-8 | EST-4 | 1.57 | 7.53
| Request status-change operation and transition rules | 9.6 | 16.8 | Accept Open to In progress, In progress to Done, and Done to Open only; Reject all other status changes without changing the record; Unknown request ID returns not found; Missing status-change body and unrecognized status value return errors without changing the record; Do not expose edit or delete operations (8 rules: 3 allowed transitions, rejection of other transitions, unknown-ID handling, missing-body handling, unrecognized-status handling, and no edit/delete operations: typical, matching the approved typical task. [be-rules backend 8-14 h, typical]) | Factory | REQ-4, REQ-8, REQ-9 | EST-5 | 1.57 | 7.53
| Development Total Efforts (in hours) | 27.26 | 49.73 |  |  |  |  | 4.58 | 21.95
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0 |  |  |  |  | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | None | 0 | 0 | No research task in this estimate |  |  |  | 0 | 0
| Research Total Efforts (in hours) | 0 | 0 |  |  |  |  | 0 | 0
S.No | Assumptions & Constraints
1 | Spec question Q-6: Should the 1280 px table-layout target be configurable, or remain the fixed target specified for this release? → Keep 1280 px as the fixed table-layout target. (answered)
2 | Spec question Q-7: Should the request detail screen add states for loading a request and for failures other than not-found? → Keep the specified detail behavior: show the request on success and “Request not found.” for an unknown ID; add no other fetch states. (answered)
3 | Spec question Q-8: How should AC-1.1 verify that a newly created request can be retrieved? → Compare the create response with a separate get-by-ID API response. (answered)
4 | No design was drawn for this estimate (it was left out at the start): the UI tasks are sized from the requirements alone, with no approved screens behind them, so their range is wider. A build from this estimate draws the design and has it approved before its plan.
5 | Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
6 | Split before the build: EST-4, EST-5, EST-6 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).
S.No | Risks
1 | Estimates will increase in case of change in requirement
2 | EST-1 Request data model, migrations, persistence, and seed data: the estimators disagree, so its range is wide
3 | EST-2 List requests API: the estimators disagree, so its range is wide
4 | EST-3 Get request by ID API: the estimators disagree, so its range is wide
5 | EST-4 Create request operation and validation rules: the estimators disagree, so its range is wide
6 | EST-5 Request status-change operation and transition rules: the estimators disagree, so its range is wide

## Dev Mobile Estimates
Development Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
Not in scope: no work in this estimate
| Grand Total (in hours) | 0 | 0 | Sum of development, other activities and research efforts. |  |  | API total ($) | 0 | 0
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
| None | 0 | 0 |  |  |  |  | 0 | 0
| Development Total Efforts (in hours) | 0 | 0 |  |  |  |  | 0 | 0
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0 |  |  |  |  | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | None | 0 | 0 | No research task in this estimate |  |  |  | 0 | 0
| Research Total Efforts (in hours) | 0 | 0 |  |  |  |  | 0 | 0

## Dev Web Estimates
Development Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
| Grand Total (in hours) | 35.26 | 59.28 | Sum of development, other activities and research efforts. |  |  | API total ($) | 5.61 | 26.94
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | Requests list and request creation | 14.98 | 24.96 |  |  |  |  | 2.37 | 11.38
| Requests list screen | 9.36 | 15.6 | Hive Works wordmark and signed-in demo-user initials SC; Status filter choices All, Open, In progress, and Done; All selected initially; Newest-first request list, with stacked cards at 375 px and table rows at 1280 px; no horizontal page scroll at those widths; New request button; Loading state “Loading requests…”; empty state “No requests here.”; load-error state “Could not load requests.” with Retry button; Selecting a filter loads its list; returning from detail retains the selected filter and refreshes the list; After successful creation, show the new Open request at the top and select All; Created date displayed without time or timezone, in a date-only format such as “8 Oct 2026”; Status and priority badges use the specified colors and include readable text labels; Every control is keyboard reachable; text meets WCAG AA contrast (One status filter on a newest-first list, with loading/empty/error states and filter-retention behavior: typical. Responsive presentation and shared UI factors are not counted again beyond the shell. [ui-list web 6-10 h, verify hard x1.3, context partial x1.2]) | Factory | REQ-10, REQ-11, REQ-13, REQ-16, REQ-21, REQ-22, REQ-23 | EST-7 | 1.48 | 7.11
| New request dialog | 5.62 | 9.36 | Dialog with labeled Title, Area, Priority, and Description fields; Priority defaults to Normal; Create and Cancel controls; Show a field's validation error under that field and keep the dialog open; include the Title error “Title must be 3 to 80 characters.” for a two-character title; On non-validation create failure, show “Could not create request.”, retain entered values, and allow retry through Create; On successful creation, close the dialog and show the new Open request through the Requests list's All filter; Every field is labeled and every control is keyboard reachable (4 labeled fields with validation and submit/cancel behavior: small (up to 5 fields). Dialog error and retry states do not add fields. [ui-form web 6-10 h, small x0.6, verify hard x1.3, context partial x1.2]) | Factory | REQ-7, REQ-12, REQ-13, REQ-14, REQ-15, REQ-22 | EST-8 | 0.89 | 4.27
2 | Request detail and status changes | 7.8 | 12.48 |  |  |  |  | 1.2 | 5.78
| Request detail screen | 7.8 | 12.48 | Back link; request title, area, priority badge, status badge, created date, and description or “No description.”; Show “Request not found.” and a link back to Requests for an unknown ID; Show Start work for Open, Mark done for In progress, and Reopen for Done; After a successful status change, show the new status badge and corresponding next action; on failure show “Could not update the request.” and retain the prior status badge; Status and priority badges use the specified colors and include readable text labels; Created date displayed without time or timezone, in a date-only format such as “8 Oct 2026”; Every control is keyboard reachable; text meets WCAG AA contrast (A detail view with one status-dependent action at a time, plus not-found and update-failure states: typical. [ui-detail web 5-8 h, verify hard x1.3, context partial x1.2]) | Factory | REQ-11, REQ-17, REQ-18, REQ-19, REQ-20, REQ-21, REQ-22, REQ-23 | EST-9 | 1.2 | 5.78
3 | Visual presentation and accessibility | 12.48 | 21.84 |  |  |  |  | 2.04 | 9.78
| Web application shell and light theme | 12.48 | 21.84 | Browser-accessible web application shell and page layout; One light theme with sans-serif text, neutral background, and near-black text (One browser layout with an explicit light theme and shared responsive/accessibility UI factors: typical. The closest approved shell was small; this scope includes the explicit theme and shared UI factors. [ui-shell web 8-14 h, verify hard x1.3, context partial x1.2]) | Factory | REQ-1, REQ-21 | EST-6 | 2.04 | 9.78
| Development Total Efforts (in hours) | 35.26 | 59.28 |  |  |  |  | 5.61 | 26.94
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0 |  |  |  |  | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | None | 0 | 0 | No research task in this estimate |  |  |  | 0 | 0
| Research Total Efforts (in hours) | 0 | 0 |  |  |  |  | 0 | 0
S.No | Assumptions & Constraints
1 | Spec question Q-6: Should the 1280 px table-layout target be configurable, or remain the fixed target specified for this release? → Keep 1280 px as the fixed table-layout target. (answered)
2 | Spec question Q-7: Should the request detail screen add states for loading a request and for failures other than not-found? → Keep the specified detail behavior: show the request on success and “Request not found.” for an unknown ID; add no other fetch states. (answered)
3 | Spec question Q-8: How should AC-1.1 verify that a newly created request can be retrieved? → Compare the create response with a separate get-by-ID API response. (answered)
4 | No design was drawn for this estimate (it was left out at the start): the UI tasks are sized from the requirements alone, with no approved screens behind them, so their range is wider. A build from this estimate draws the design and has it approved before its plan.
5 | Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
6 | Split before the build: EST-4, EST-5, EST-6 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).
S.No | Risks
1 | Estimates will increase in case of change in requirement

## QA Estimates
QA Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
| Grand Total Efforts (in hours) | 13 | 24.2 | Sum of QA and Misc. |  |  | API total ($) | 1.49 | 7.18
S.No | Estimation Summary | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | Test Plan/Strategy | 0 | 0 | Test planning, with the test plan, strategy and traceability matrix as outputs. Not sized in this estimate |  |  |  | 0 | 0
2 | Set up of Test Environments | 0 | 0 | Setting up code and white box test environments. Not sized in this estimate |  |  |  | 0 | 0
3 | Validation and Smoke test cases | 3.6 | 7.2 | Test cases to execute while debugging and white box testing |  |  |  | 0.64 | 3.08
| Automated request business-rule test cases | 3.6 | 7.2 | Automated cases for valid creation with Open status; missing and too-short title rejection; missing area rejection; too-long description rejection; Automated cases for all three allowed status transitions and rejection of a disallowed transition; Automated cases for filtered newest-first listing and unknown-ID not-found behavior (3 test flows: creation/validation, status transitions, and filtered listing/not-found behavior: typical. [qa-cases qa 3-6 h, verify easy x0.9]) | Factory | REQ-24 | EST-10 | 0.64 | 3.08
4 | Validation testing | 5.4 | 9 | Testing cycles; the detail is below |  |  |  | 0.85 | 4.1
| Testing Cycle 1 | 5.4 | 9 |  |  |  |  | 0.85 | 4.1
5 | Smoke testing | 0 | 0 | Smoke testing after each deployment, including preparation. Not sized in this estimate |  |  |  | 0 | 0
6 | Multi Browser Compatibility testing | 0 | 0 | Browser, OS and device compatibility. Not sized in this estimate |  |  |  | 0 | 0
7 | UAT | 4 | 8 | Client user acceptance testing support |  |  |  | 0 | 0
| Client acceptance testing | 4 | 8 | Client UAT is a required human acceptance activity and does not deliver a specification requirement. (One client acceptance and regression round: typical, matching the approved typical task. [qa-uat qa 4-8 h, typical]) | Human |  | EST-12 | 0 | 0
8 | Misc. Optional testing | 0 | 0 | Other testing named in the breakdown, and supervisor gate time. Not sized in this estimate |  |  |  | 0 | 0
| Total QA Efforts | 13 | 24.2 | Total hours of QA |  |  |  | 1.49 | 7.18
S.No | Validation Testing | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
Testing Cycle 1
1 | Automated list-to-completion end-to-end test | 5.4 | 9 | Run the list, create, open, Start work, Mark done, and Done-filter workflow; Verify the created request appears at the top, then appears in the Done-filtered list after completion (One multi-step list-to-completion workflow spanning list, create, detail, status changes and the Done filter; broader than a short flow: typical, matching the approved typical task. [qa-e2e qa 6-10 h, verify easy x0.9]) | Factory | REQ-24 | EST-11 | 0.85 | 4.1
| Total Testing Cycle 1 | 5.4 | 9 | Sum of testing cycle 1 |  |  |  | 0.85 | 4.1
S.No | Assumptions & Constraints
1 | Spec question Q-6: Should the 1280 px table-layout target be configurable, or remain the fixed target specified for this release? → Keep 1280 px as the fixed table-layout target. (answered)
2 | Spec question Q-7: Should the request detail screen add states for loading a request and for failures other than not-found? → Keep the specified detail behavior: show the request on success and “Request not found.” for an unknown ID; add no other fetch states. (answered)
3 | Spec question Q-8: How should AC-1.1 verify that a newly created request can be retrieved? → Compare the create response with a separate get-by-ID API response. (answered)
4 | No design was drawn for this estimate (it was left out at the start): the UI tasks are sized from the requirements alone, with no approved screens behind them, so their range is wider. A build from this estimate draws the design and has it approved before its plan.
5 | Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
6 | Split before the build: EST-4, EST-5, EST-6 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).
S.No | Risks
1 | Estimates will increase in case of change in requirement
2 | EST-10 Automated request business-rule test cases: the estimators disagree, so its range is wide
3 | EST-11 Automated list-to-completion end-to-end test: the estimators disagree, so its range is wide

## Design Estimates
Design Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
Not in scope: no work in this estimate
| Grand Total (in hours) | 0 | 0 | Sum of development, other activities and research efforts. |  |  | API total ($) | 0 | 0
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
| None | 0 | 0 |  |  |  |  | 0 | 0
| Development Total Efforts (in hours) | 0 | 0 |  |  |  |  | 0 | 0
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0 |  |  |  |  | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | None | 0 | 0 | No research task in this estimate |  |  |  | 0 | 0
| Research Total Efforts (in hours) | 0 | 0 |  |  |  |  | 0 | 0

## Other Estimates
Other Estimates for Maintenance Request
2026-10-10
by Ahsan Raza
GD
Not in scope: no work in this estimate
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| GD TOTAL | 0 | 0 |  |  |  |  | 0 | 0
PM
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | Client liaison and project management | 4 | 8 | Required human client liaison and project-management overhead; factory planning and coordination of its own work are excluded. (Client liaison, scope decisions and sign-offs across the project; assuming about a month of delivery: typical, matching the approved typical task. [pm-management pm 4-8 h, typical]) | Human |  | EST-13 | 0 | 0
| PM TOTAL | 4 | 8 |  |  |  |  | 0 | 0
PDM
Not in scope: no work in this estimate
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| PDM TOTAL | 0 | 0 |  |  |  |  | 0 | 0
Cross-cutting
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | API min ($) | API max ($)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| Cross-cutting TOTAL | 0 | 0 |  |  |  |  | 0 | 0

## All Tasks
All tasks: Maintenance Request
Filter or sort any column. The Total row adds up only the rows the filter shows.
Task id | Task | Track | Module | Executor | Requirement id(s) | Minimum | Maximum | API min ($) | API max ($)
EST-1 | Request data model, migrations, persistence, and seed data | Backend | Request data and HTTP API | Factory | REQ-1, REQ-2, REQ-3, REQ-6 | 2.88 | 5.76 | 0.51 | 2.46
EST-2 | List requests API | Backend | Request data and HTTP API | Factory | REQ-2, REQ-4, REQ-5 | 3.24 | 6.48 | 0.58 | 2.77
EST-3 | Get request by ID API | Backend | Request data and HTTP API | Factory | REQ-1, REQ-3, REQ-4, REQ-20 | 1.94 | 3.89 | 0.35 | 1.66
EST-4 | Create request operation and validation rules | Backend | Request data and HTTP API | Factory | REQ-4, REQ-6, REQ-7, REQ-8 | 9.6 | 16.8 | 1.57 | 7.53
EST-5 | Request status-change operation and transition rules | Backend | Request data and HTTP API | Factory | REQ-4, REQ-8, REQ-9 | 9.6 | 16.8 | 1.57 | 7.53
EST-6 | Web application shell and light theme | Web | Visual presentation and accessibility | Factory | REQ-1, REQ-21 | 12.48 | 21.84 | 2.04 | 9.78
EST-7 | Requests list screen | Web | Requests list and request creation | Factory | REQ-10, REQ-11, REQ-13, REQ-16, REQ-21, REQ-22, REQ-23 | 9.36 | 15.6 | 1.48 | 7.11
EST-8 | New request dialog | Web | Requests list and request creation | Factory | REQ-7, REQ-12, REQ-13, REQ-14, REQ-15, REQ-22 | 5.62 | 9.36 | 0.89 | 4.27
EST-9 | Request detail screen | Web | Request detail and status changes | Factory | REQ-11, REQ-17, REQ-18, REQ-19, REQ-20, REQ-21, REQ-22, REQ-23 | 7.8 | 12.48 | 1.2 | 5.78
EST-10 | Automated request business-rule test cases | QA | Automated verification | Factory | REQ-24 | 3.6 | 7.2 | 0.64 | 3.08
EST-11 | Automated list-to-completion end-to-end test | QA | Automated verification | Factory | REQ-24 | 5.4 | 9 | 0.85 | 4.1
EST-12 | Client acceptance testing | QA | Automated verification | Human |  | 4 | 8 | 0 | 0
EST-13 | Client liaison and project management | PM | Automated verification | Human |  | 4 | 8 | 0 | 0
| Total (rows shown) |  |  |  |  | 79.52 | 141.21 | 11.68 | 56.07

## Confidence
Delivery model | agentic
Size band | M
Uncertainty | high
Cost confidence | partial
Benchmark records | 21
Flagged tasks (estimators disagree) | 7
Spec sha | e2059a0dfaf708960598d4f8255b9841bd06bd97f1f8a91187b28850ce6a85d2
Breakdown sha | 9f6a33e8048b820d68f3887c921710cdce802e8b48d6503e0d4781362d0669c7
Task catalogue | 2026-10-06.1 (stack dotnet)
Catalogue status | reference hours, not yet measured
Factory hours basis | cold-start: each task's sized hours, a reference size, until this factory has built enough tasks of its class (3 or more)
API cost by phase | Based on | Ledger runs | Eval runs
planning ($0.51-7.07) | measured: p10-p90 of 8 runs (8 ledger) | 8 | 0
breakdown-estimate ($0.47-0.95) | measured: p10-p90 of 3 runs (3 ledger) | 3 | 0
build ($11.62-54.33) | measured: p10-p90 of 6 runs (3 ledger, 3 eval) | 3 | 3
verification ($0.06-1.74) | measured: p10-p90 of 4 runs (2 ledger, 2 eval) | 2 | 2

## Anchors
Anchors
Task | Title | Min (h) | Max (h) | Why a fair reference
EST-1 | Request data model, migrations, persistence, and seed data | 2.88 | 5.76 | 1 entity (Request) with migration, persistence and seed data; seed rows do not add entities: small. [be-data backend 4-8 h, small x0.6] (Median of the estimators; the lead estimator read 2.4-4.8 h, and the ratios multiply that reading.)
EST-2 | List requests API | 3.24 | 6.48 | One optional status filter plus newest-first ordering and status counts: typical. The filter makes this larger than the closest approved small endpoint, which had no filter. [be-endpoint backend 3-6 h, verify easy x0.9] (Median of the estimators; the lead estimator read 2.7-5.4 h, and the ratios multiply that reading.)
EST-4 | Create request operation and validation rules | 9.6 | 16.8 | 11 distinct rules: 3 creation assignments, 4 field validations, field-specific errors, fixed fields, no deletion, and an operation allowlist: large, matching the approved large task. [be-rules backend 8-14 h, large x1.6] (Median of the estimators; the lead estimator read 12.8-22.4 h, and the ratios multiply that reading.)
EST-6 | Web application shell and light theme | 12.48 | 21.84 | One browser layout with an explicit light theme and shared responsive/accessibility UI factors: typical. The closest approved shell was small; this scope includes the explicit theme and shared UI factors. [ui-shell web 8-14 h, verify hard x1.3, context partial x1.2]
EST-7 | Requests list screen | 9.36 | 15.6 | One status filter on a newest-first list, with loading/empty/error states and filter-retention behavior: typical. Responsive presentation and shared UI factors are not counted again beyond the shell. [ui-list web 6-10 h, verify hard x1.3, context partial x1.2]
EST-8 | New request dialog | 5.62 | 9.36 | 4 labeled fields with validation and submit/cancel behavior: small (up to 5 fields). Dialog error and retry states do not add fields. [ui-form web 6-10 h, small x0.6, verify hard x1.3, context partial x1.2]
EST-9 | Request detail screen | 7.8 | 12.48 | A detail view with one status-dependent action at a time, plus not-found and update-failure states: typical. [ui-detail web 5-8 h, verify hard x1.3, context partial x1.2]
EST-10 | Automated request business-rule test cases | 3.6 | 7.2 | 3 test flows: creation/validation, status transitions, and filtered listing/not-found behavior: typical. [qa-cases qa 3-6 h, verify easy x0.9] (Median of the estimators; the lead estimator read 2.7-5.4 h, and the ratios multiply that reading.)
EST-11 | Automated list-to-completion end-to-end test | 5.4 | 9 | One multi-step list-to-completion workflow spanning list, create, detail, status changes and the Done filter; broader than a short flow: typical, matching the approved typical task. [qa-e2e qa 6-10 h, verify easy x0.9]
EST-12 | Client acceptance testing | 4 | 8 | One client acceptance and regression round: typical, matching the approved typical task. [qa-uat qa 4-8 h, typical]
EST-13 | Client liaison and project management | 4 | 8 | Client liaison, scope decisions and sign-offs across the project; assuming about a month of delivery: typical, matching the approved typical task. [pm-management pm 4-8 h, typical]
Task | Title | Anchor | Ratio | Reason | Min (h) | Max (h) | Executor | Flagged
EST-1 | Request data model, migrations, persistence, and seed data | EST-1 | 1 | 1 entity (Request) with migration, persistence and seed data; seed rows do not add entities: small. [be-data backend 4-8 h, small x0.6] | 2.88 | 5.76 | factory | yes
EST-2 | List requests API | EST-2 | 1 | One optional status filter plus newest-first ordering and status counts: typical. The filter makes this larger than the closest approved small endpoint, which had no filter. [be-endpoint backend 3-6 h, verify easy x0.9] | 3.24 | 6.48 | factory | yes
EST-3 | Get request by ID API | EST-2 | 0.6 | Plain get-by-ID read with a not-found case; no filters or joins: small, matching the approved small task. [be-endpoint backend 3-6 h, small x0.6, verify easy x0.9] | 1.94 | 3.89 | factory | yes
EST-4 | Create request operation and validation rules | EST-4 | 1 | 11 distinct rules: 3 creation assignments, 4 field validations, field-specific errors, fixed fields, no deletion, and an operation allowlist: large, matching the approved large task. [be-rules backend 8-14 h, large x1.6] | 9.6 | 16.8 | factory | yes
EST-5 | Request status-change operation and transition rules | EST-4 | 0.625 | 8 rules: 3 allowed transitions, rejection of other transitions, unknown-ID handling, missing-body handling, unrecognized-status handling, and no edit/delete operations: typical, matching the approved typical task. [be-rules backend 8-14 h, typical] | 9.6 | 16.8 | factory | yes
EST-6 | Web application shell and light theme | EST-6 | 1 | One browser layout with an explicit light theme and shared responsive/accessibility UI factors: typical. The closest approved shell was small; this scope includes the explicit theme and shared UI factors. [ui-shell web 8-14 h, verify hard x1.3, context partial x1.2] | 12.48 | 21.84 | factory
EST-7 | Requests list screen | EST-7 | 1 | One status filter on a newest-first list, with loading/empty/error states and filter-retention behavior: typical. Responsive presentation and shared UI factors are not counted again beyond the shell. [ui-list web 6-10 h, verify hard x1.3, context partial x1.2] | 9.36 | 15.6 | factory
EST-8 | New request dialog | EST-8 | 1 | 4 labeled fields with validation and submit/cancel behavior: small (up to 5 fields). Dialog error and retry states do not add fields. [ui-form web 6-10 h, small x0.6, verify hard x1.3, context partial x1.2] | 5.62 | 9.36 | factory
EST-9 | Request detail screen | EST-9 | 1 | A detail view with one status-dependent action at a time, plus not-found and update-failure states: typical. [ui-detail web 5-8 h, verify hard x1.3, context partial x1.2] | 7.8 | 12.48 | factory
EST-10 | Automated request business-rule test cases | EST-10 | 1 | 3 test flows: creation/validation, status transitions, and filtered listing/not-found behavior: typical. [qa-cases qa 3-6 h, verify easy x0.9] | 3.6 | 7.2 | factory | yes
EST-11 | Automated list-to-completion end-to-end test | EST-11 | 1 | One multi-step list-to-completion workflow spanning list, create, detail, status changes and the Done filter; broader than a short flow: typical, matching the approved typical task. [qa-e2e qa 6-10 h, verify easy x0.9] | 5.4 | 9 | factory | yes
EST-12 | Client acceptance testing | EST-12 | 1 | One client acceptance and regression round: typical, matching the approved typical task. [qa-uat qa 4-8 h, typical] | 4 | 8 | human
EST-13 | Client liaison and project management | EST-13 | 1 | Client liaison, scope decisions and sign-offs across the project; assuming about a month of delivery: typical, matching the approved typical task. [pm-management pm 4-8 h, typical] | 4 | 8 | human

## Traceability
Requirements and traceability
Requirement | Title | Tasks
REQ-1 | The maintenance request system shall provide a browser-accessible web front end, an HTTP API, and a database that stores request records. | EST-1, EST-3, EST-6
REQ-10 | The Requests screen shall display the Hive Works wordmark, the signed-in demo user's initials SC, a status filter with All, Open, In prog... | EST-7
REQ-11 | When a user selects a status filter or returns from request detail, the Requests screen shall load the list for the selected filter and r... | EST-7, EST-9
REQ-12 | When the user opens New request, the Requests screen shall show a dialog with Title, Area, Priority defaulting to Normal, and Description... | EST-8
REQ-13 | When valid request creation succeeds, the Requests screen shall close the dialog, select All, and show the new Open request at the top of... | EST-7, EST-8
REQ-14 | When a create field fails validation, the Requests screen shall keep the dialog open and display the field's error message under that field. | EST-8
REQ-15 | When the create API call fails for a reason other than field validation, the Requests screen shall show “Could not create request.” in th... | EST-8
REQ-16 | While requests are loading, absent for the selected filter, or fail to load, the Requests screen shall display the corresponding loading,... | EST-7
REQ-17 | When a request exists, the request detail screen shall display a back link, its title, area, priority badge, status badge, created date, ... | EST-9
REQ-18 | The request detail screen shall show Start work for Open, Mark done for In progress, and Reopen for Done. | EST-9
REQ-19 | When a status change succeeds or fails, the request detail screen shall show the new status and corresponding action only after success, ... | EST-9
REQ-2 | When an empty database is initialized, the maintenance request system shall seed exactly eight requests: four Open including exactly one ... | EST-1, EST-2
REQ-20 | When a request ID does not exist, the request detail screen shall display “Request not found.” and a link back to the Requests screen. | EST-3, EST-9
REQ-21 | The maintenance request screens shall use one light theme, one sans-serif font, a neutral background, near-black text, and the specified ... | EST-6, EST-7, EST-9
REQ-22 | The maintenance request screens shall show request dates as date-only values, use stacked cards at 375 px and table rows at the fixed 128... | EST-7, EST-8, EST-9
REQ-23 | The maintenance request system shall display created dates as date-only values such as “8 Oct 2026” without a time or timezone. | EST-7, EST-9
REQ-24 | The maintenance request application shall include automated tests for the request business rules and an end-to-end list-to-completion wor... | EST-10, EST-11
REQ-3 | The maintenance request system shall persist request records across browser reloads and application restarts. | EST-1, EST-3
REQ-4 | The API shall expose exactly four request operations and no others: list requests, create a request, get a request by ID, and change a re... | EST-2, EST-3, EST-4, EST-5
REQ-5 | When a client lists requests, the API shall return all requests or only requests matching one requested status, ordered newest first. | EST-2
REQ-6 | When a client creates a valid request, the maintenance request system shall assign an ID and UTC creation time and set its status to Open. | EST-1, EST-4
REQ-7 | When a client submits a request for creation, the maintenance request system shall require a title trimmed to 3 to 80 characters, an area... | EST-4, EST-8
REQ-8 | The API shall keep title, area, priority, and description fixed after creation and reject attempts to change those fields or delete a req... | EST-4, EST-5
REQ-9 | The maintenance request API shall accept only Open to In progress, In progress to Done, and Done to Open status transitions, reject all o... | EST-5
Tasks with no requirement (named overheads)
EST-12 | Client acceptance testing | Client UAT is a required human acceptance activity and does not deliver a specification requirement.
EST-13 | Client liaison and project management | Required human client liaison and project-management overhead; factory planning and coordination of its own work are excluded.

## Parameters
Assumed parameters and gate time (all editable, all assumed)
Parameter | Min | Max
Clarify minutes per question | 2 | 5
Approval minutes per section | 3 | 8
PR review minutes, low risk | 10 | 20
PR review minutes, medium risk | 20 | 40
PR review minutes, high risk | 40 | 90
Parked-run rate | 0.05 | 0.15
Parked-run intervention minutes | 20 | 60
Waiver minutes | 5 | 15
Cold-start dollars per task | 1.3 | 1.8
Estimator tolerance | 0.5
Tasks per PR | 2
Hours per day | 8
Hours per week | 40
Agentic build factor | 1.25
Gate hours in this estimate
None: the solely agentic model has no supervisor gates
No rates were given, so there is no cost overlay.

## Gates
Estimate gates and waivers
Gate | Result | Details
estimate.e1-readiness | passed | 24 requirements, lint, critic and round trip clean (3 problems settled by questions), no open questions
estimate.e2-req-to-task | passed | all 24 requirements have a task
estimate.e3-task-to-req | passed | every task cites a requirement or a named overhead
estimate.e2c-task-kind | passed | every task has a catalogue kind that fits its track (catalogue 2026-10-06.1)
estimate.e4-checklist | passed | 14 checklist items each in, or out with a reason
estimate.e1c-design-coverage | passed | no approved screens, and no task cites one
estimate.e5-consistency | passed | similar tasks are within tolerance
estimate.e6-lint | passed | totals, ratios and costs recompute cleanly
estimate.e7-approval | passed | approved by mhamza
Waivers
Gates | Step | Waived by and why
None