## Summary
Folio3 Project Estimation
Parts Quick Order
Summary of Estimates
Client Name | Demo Garage
Project Manager | mhamza
Date | 2026-10-05
Version | 1
Efforts (in hours)
Task Summary | Minimum | Maximum | Comments | Avg | Resources | Weeks
Backend Development Estimates | 25.58 | 42.81 | Grand total of the Backend sheet | 34.2 | 1 | 0.86
Mobile Development Estimates | 0 | 0 | Grand total of the Mobile sheet | 0 | 1 | 0
Admin Development Estimates | 4.68 | 9.36 | Grand total of the Web / Admin sheet | 7.02 | 1 | 0.18
QA Estimates | 4 | 8 | Grand total of the QA sheet | 6 | 1 | 0.15
GD Estimates | 0 | 0 | Other Estimates sheet | 0 | 1 | 0
PM Estimates | 16 | 24 | Other Estimates sheet | 20 | 1 | 0.5
PDM Estimates | 0 | 0 | Other Estimates sheet | 0 | 1 | 0
Cross-cutting Estimates | 0 | 0 | Other Estimates sheet: deployment, documentation and the like | 0 | 1 | 0
Design Estimates | 0 | 0 | Counted in the total only when Design is switched on below | 0 | 1 | 0
Total | 50.26 | 84.17 |  | 67.22
List of Special Considerations, where applicable:
Tasks | Action |  | Comments
Application type (mobile, desktop, web) | Backend + Web |  | From the tracks that have work
Platforms/OS supported | Not specified |  | Confirm with the client
Browsers supported | Assumed: The latest two versions of Chrome, Edge, Safari and Firefox. |  | Factory assumption ASM-17, confirm with the client
Deployment (cloud, dedicated server, enterprise internal network) | Not specified |  | Confirm with the client
Performance, Load requirements | Assumed: Up to 1,000 users and 100,000 records in the first year. |  | Factory assumption ASM-16, confirm with the client
Security requirements | Not specified |  | Confirm with the client
Documentation requirements | Not specified |  | Confirm with the client
Other custom? | No
Parameters
Include Design in total | Yes
Hours per week | 40
Feedback rounds | 2
Stack chosen by | client
Delivery model | Solely agentic
Size band | M
API credit cost (USD)
Phase | Min ($) | Max ($)
planning | 0.64 | 2.92
design | 0.05 | 7.3
breakdown-estimate | 0.07 | 0.09
build | 11.7 | 16.2
verification | 5.85 | 8.1
API credit cost total | 18.31 | 34.61
Confidence | cold-start (6 measured records)
Elapsed time
Planning (minutes) | 35
Build critical path (days) | 8.58 | 14.31
Assumptions
Does the 'Place order' button also need the cart to have at least one line, or is that already covered because checkout is hidden when the cart is empty? → assumed: Covered already: checkout is hidden when the cart is empty, and the API also refuses an order with no lines
Does placing (or cancelling) an order change the stock quantity in the existing parts database? → assumed: No: stock is read-only and orders never change it
What happens when a cart quantity is more than the current stock (or the part is now out of stock) at the moment the buyer presses 'Place order'? → assumed: The API checks stock again, rejects the order, lowers the affected lines to the stock now available with 'Only n available', and keeps the cart
Where is the cart kept? → assumed: In the browser's local storage for the signed-in buyer (kept across page reloads on the same device)
How does the API find out which buyer is making a request through the existing company login? → assumed: The API checks the existing company login's session token or cookie and reads the buyer ID from it
Nothing in this work moves an order to Packed, Dispatched or Delivered (no admin screens, no integrations). How do statuses change after Placed? → assumed: Staff update the status directly in the database, outside this work; the portal only shows it
Which unit price is saved on an order line, and what does the order 'total' include? → assumed: The part's current price when the order is placed; total = subtotal + delivery charge
How are 'ORD-' + 6-digit order numbers generated? → assumed: Sequential from a database sequence, zero-padded (ORD-000001)
Should the delivery prices (£0 / £9.99), the stock thresholds (5) and the page size (20) be fixed in the code or set in configuration? → assumed: Fixed constants in the code
What happens if the order's status changes from Placed (e.g. to Packed) after the buyer opened it but before they confirm cancelling? → assumed: The API cancels only if the status is still Placed; otherwise it refuses, shows a message and refreshes the order
What happens if placing an order fails (network or server error)? → assumed: Show an error message, keep the cart and checkout details, and let the buyer try again
What happens when a quantity is set to 0, left blank, set above 99, or isn't a whole number? → assumed: Set it to the nearest value in range (blank or 0 becomes 1, above 99 becomes 99)
What do 'cart count' in the header and 'number of items' in My orders count? → assumed: The total of all quantities (2 filters + 1 pad = 3)
How do the parts list filters and sort order work? → assumed: One category and one brand at a time (each with 'All'), brands taken from the parts data, sorted by name A–Z, back to page 1 whenever the search or a filter changes
Is the delivery address remembered from the buyer's previous order? → assumed: No: typed fresh for each order
Under what conditions is the 2-second load target measured, and how many buyers and orders are expected? → assumed: Up to 1,000 users and 100,000 records in the first year.
Which browsers must be supported? → assumed: The latest two versions of Chrome, Edge, Safari and Firefox.
Are orders written to the same PostgreSQL database that holds the existing parts? → assumed: Yes: new orders and order-lines tables in the same database, referring to parts by part number
Spec question Q-1: If a part in the cart now has 0 stock, what should happen to that cart line? (One rule says the quantity can never go below 1. Another says it can never go above stock.) → Remove the line and show "<part name> is now out of stock" (assumed by the factory, hands-off)
Spec question Q-2: If the buyer retries after a network error but the first order was actually saved, how should we stop the order being placed twice? → Disable "Place order" while a request is in progress, and on a network error tell the buyer to check My orders before retrying (assumed by the factory, hands-off)
Spec question Q-3: The cart keeps a saved copy of each price, but orders are charged at the current price. How should the cart handle a price that has changed? → Fetch the current prices from the parts API when the cart opens, and show only those (assumed by the factory, hands-off)
Spec question Q-4: Should the spec keep a separate requirement that the API rejects requests with no valid company-login session (status 401)? The request doesn't mention this. → Leave it out and rely on the existing company login as-is (assumed by the factory, hands-off)
Spec question Q-5: When the cart opens and the request to the parts API for current prices fails (network or server error), what should the cart show and allow? The saved prices must never be shown. → Show the cart lines without prices or totals, show an error message with a "Try again" button, and hide checkout until current prices load (assumed by the factory, hands-off)
Open risk: ASM-26 and AC-41.1 need GET /api/parts filtered to the cart's part numbers in a single call, but REQ-2/4/5 and ASM-19 only define q (at least 2 characters, substring match), category, brand and page, so no defined parameter can fetch exactly the cart's parts.
Open risk: When the cart opens, only lines whose part now has 0 stock are handled; a line whose stock has dropped but is still above 0 (cart quantity 5, stock now 2) is left unclamped until the 409 at Place order, and REQ-14's clamp only runs when the buyer edits the quantity.
Open risk: The order is charged at the server's current price, but the price can change between cart refresh and Place order; nothing says the buyer is told or asked to confirm, so the saved total can differ from the total on screen (payments risk).
Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
Split before the build: EST-2, EST-5, EST-8, EST-19 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).

## Dev Backend Estimates
Development Estimates for Parts Quick Order
2026-10-05
by mhamza
| Grand Total (in hours) | 25.58 | 42.81 | Sum of development, other activities and research efforts.
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | Portal shell, sign-in wiring, navigation, accessibility and responsive layout | 25.58 | 42.81 |  |  |  |  | 25.58 | 42.81
| Buyer identity from the existing company login session | 13.1 | 20.97 | check the existing company login's session token or cookie on every API request; read the buyer ID from the session and pass it to the parts and orders APIs; expose the buyer ID to the portal for the per-buyer cart key; human step: get access to and details of the company login session format (One sign-in method (reusing the existing company session) and one buyer role: small [be-auth backend 10-16 h, small x0.6, external-dependency x1.4, verify hard x1.3, context partial x1.2]) | Joint | REQ-27 | EST-2 | 13.1 | 20.97
| Environments, CI/CD and monitoring | 12.48 | 21.84 | Environment and pipeline setup; delivers no requirement directly (Dev, staging and production with a CI pipeline and monitoring, but no infrastructure as code is asked for. That falls between typical and large, so the smaller step: typical [ops-setup backend 8-14 h, verify hard x1.3, context partial x1.2]) | Joint |  | EST-19 | 12.48 | 21.84
2 | Find parts (search, filters, paging, stock state, add to cart) | 0 | 0 |  |  |  |  | 4.62 | 9.24
| GET /api/parts: search, filters, paging, stock state | 0 | 0 | sorted by name A–Z, 20 per page (fixed constant), page parameter, total count; fields: image (or null), name, partNumber, brand, price in GBP with 2 decimals, stockState, stock as a whole number; stockState: "In stock" at 5 or more, "Low stock (n left)" at 1–4, "Out of stock" at 0; q: case-insensitive contains on name or part number, applied only at 2+ characters; category and brand filters, one each, "All" means no filter, combined with q; no match returns 200 with an empty list and total 0; p95 under 500 ms with 5,000 parts (Search plus 2 filters (category, brand), paging, sorting and a derived stock state, with no joins over 3+ tables or aggregates: typical [be-endpoint backend 3-6 h, typical]) | Factory | REQ-2, REQ-3, REQ-4, REQ-5, REQ-7, REQ-38 | EST-3 | 3 | 6
| GET /api/parts/brands: brand list from parts data | 0 | 0 | distinct brands taken from the parts data, sorted (One plain distinct read of brands, with no filters or paging: small [be-endpoint backend 3-6 h, small x0.6, verify easy x0.9]) | Factory | REQ-5 | EST-4 | 1.62 | 3.24
3 | Checkout and placing an order | 0 | 0 |  |  |  |  | 21.31 | 35.06
| Data model: orders, order lines, order number sequence, parts indexes and seed data | 0 | 0 | orders table in the existing PostgreSQL database: buyer ID, order number, date placed, delivery address, delivery option (STANDARD/NEXT_DAY), total, status; order_lines table: order, part number (refers to parts by part number), quantity, unit price; status values Placed, Packed, Dispatched, Delivered, Cancelled; database sequence for ORD- + 6 zero-padded digits (ORD-000001); indexes on orders (buyer ID, date placed, status) for 100,000 records; indexes on parts name / part number / category / brand for search with 5,000 parts; seed of 5,000 parts for performance testing; migrations (2 new tables (orders, order_lines) plus a sequence, with indexes and a parts seed on an existing table. That is up to 3 entities and no existing data is migrated: small [be-data backend 4-8 h, small x0.6, verify easy x0.9, context partial x1.2]) | Factory | REQ-20, REQ-28, REQ-38 | EST-1 | 2.59 | 5.18
| Orders API: create with validation, list, detail, scoped to the buyer | 0 | 0 | POST /api/orders returns 201 with orderNumber, status Placed, total; 400 with an error field naming the input for: no lines, quantity outside 1–99, unknown part number, address outside 5–200 characters, missing or unknown delivery option; no order saved; GET /api/orders: only the buyer's orders, newest first, with orderNumber, datePlaced, itemCount (total of quantities), total, status; GET /api/orders?status=: status filter; empty list with 200 when the buyer has no orders; GET /api/orders/{orderNumber}: lines (part number, name, quantity, unit price), address, delivery option, total, status; 404 for another buyer's order (Order of about 7 fields with order lines and a part reference (2 relations), but it also needs custom queries (status filter, itemCount sum, buyer scoping, lookup by order number) and 6 validation rules: large [be-crud backend 8-12 h, large x1.6, verify easy x0.9]) | Factory | REQ-20, REQ-21, REQ-27, REQ-28, REQ-29, REQ-30, REQ-35 | EST-5 | 11.52 | 17.28
| Order rules: pricing, totals, numbering, stock check, cancel state machine | 0 | 0 | unit price = the part's current price when placed; any price sent by the client is ignored; total = subtotal + delivery charge (Standard £0.00, Next day £9.99, fixed constants); sequential order number ORD-000001, ORD-000002 … from the sequence; stock check at placement: 409 listing each affected part number with available stock; no order saved (transaction); stock quantity in parts never changed on place or cancel; POST /api/orders/{orderNumber}/cancel: sets Cancelled and returns 200 only if still Placed (conditional update); 409 with an error message when no longer Placed, status left unchanged; 404 when cancelling another buyer's order (8 rules (price snapshot, total and delivery charge, numbering, transactional stock check, stock untouched, conditional cancel, 409, 404) and only a Placed to Cancelled transition: typical [be-rules backend 8-14 h, typical]) | Factory | REQ-20, REQ-22, REQ-25, REQ-27, REQ-33, REQ-34 | EST-6 | 7.2 | 12.6
| Development Total Efforts (in hours) | 25.58 | 42.81
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | None | 0 | 0 | No research task in this estimate
| Research Total Efforts (in hours) | 0 | 0
S.No | Assumptions & Constraints
1 | Does the 'Place order' button also need the cart to have at least one line, or is that already covered because checkout is hidden when the cart is empty? → assumed: Covered already: checkout is hidden when the cart is empty, and the API also refuses an order with no lines
2 | Does placing (or cancelling) an order change the stock quantity in the existing parts database? → assumed: No: stock is read-only and orders never change it
3 | What happens when a cart quantity is more than the current stock (or the part is now out of stock) at the moment the buyer presses 'Place order'? → assumed: The API checks stock again, rejects the order, lowers the affected lines to the stock now available with 'Only n available', and keeps the cart
4 | Where is the cart kept? → assumed: In the browser's local storage for the signed-in buyer (kept across page reloads on the same device)
5 | How does the API find out which buyer is making a request through the existing company login? → assumed: The API checks the existing company login's session token or cookie and reads the buyer ID from it
6 | Nothing in this work moves an order to Packed, Dispatched or Delivered (no admin screens, no integrations). How do statuses change after Placed? → assumed: Staff update the status directly in the database, outside this work; the portal only shows it
7 | Which unit price is saved on an order line, and what does the order 'total' include? → assumed: The part's current price when the order is placed; total = subtotal + delivery charge
8 | How are 'ORD-' + 6-digit order numbers generated? → assumed: Sequential from a database sequence, zero-padded (ORD-000001)
9 | Should the delivery prices (£0 / £9.99), the stock thresholds (5) and the page size (20) be fixed in the code or set in configuration? → assumed: Fixed constants in the code
10 | What happens if the order's status changes from Placed (e.g. to Packed) after the buyer opened it but before they confirm cancelling? → assumed: The API cancels only if the status is still Placed; otherwise it refuses, shows a message and refreshes the order
11 | What happens if placing an order fails (network or server error)? → assumed: Show an error message, keep the cart and checkout details, and let the buyer try again
12 | What happens when a quantity is set to 0, left blank, set above 99, or isn't a whole number? → assumed: Set it to the nearest value in range (blank or 0 becomes 1, above 99 becomes 99)
13 | What do 'cart count' in the header and 'number of items' in My orders count? → assumed: The total of all quantities (2 filters + 1 pad = 3)
14 | How do the parts list filters and sort order work? → assumed: One category and one brand at a time (each with 'All'), brands taken from the parts data, sorted by name A–Z, back to page 1 whenever the search or a filter changes
15 | Is the delivery address remembered from the buyer's previous order? → assumed: No: typed fresh for each order
16 | Under what conditions is the 2-second load target measured, and how many buyers and orders are expected? → assumed: Up to 1,000 users and 100,000 records in the first year.
17 | Which browsers must be supported? → assumed: The latest two versions of Chrome, Edge, Safari and Firefox.
18 | Are orders written to the same PostgreSQL database that holds the existing parts? → assumed: Yes: new orders and order-lines tables in the same database, referring to parts by part number
19 | Spec question Q-1: If a part in the cart now has 0 stock, what should happen to that cart line? (One rule says the quantity can never go below 1. Another says it can never go above stock.) → Remove the line and show "<part name> is now out of stock" (assumed by the factory, hands-off)
20 | Spec question Q-2: If the buyer retries after a network error but the first order was actually saved, how should we stop the order being placed twice? → Disable "Place order" while a request is in progress, and on a network error tell the buyer to check My orders before retrying (assumed by the factory, hands-off)
21 | Spec question Q-3: The cart keeps a saved copy of each price, but orders are charged at the current price. How should the cart handle a price that has changed? → Fetch the current prices from the parts API when the cart opens, and show only those (assumed by the factory, hands-off)
22 | Spec question Q-4: Should the spec keep a separate requirement that the API rejects requests with no valid company-login session (status 401)? The request doesn't mention this. → Leave it out and rely on the existing company login as-is (assumed by the factory, hands-off)
23 | Spec question Q-5: When the cart opens and the request to the parts API for current prices fails (network or server error), what should the cart show and allow? The saved prices must never be shown. → Show the cart lines without prices or totals, show an error message with a "Try again" button, and hide checkout until current prices load (assumed by the factory, hands-off)
24 | Open risk: ASM-26 and AC-41.1 need GET /api/parts filtered to the cart's part numbers in a single call, but REQ-2/4/5 and ASM-19 only define q (at least 2 characters, substring match), category, brand and page, so no defined parameter can fetch exactly the cart's parts.
25 | Open risk: When the cart opens, only lines whose part now has 0 stock are handled; a line whose stock has dropped but is still above 0 (cart quantity 5, stock now 2) is left unclamped until the 409 at Place order, and REQ-14's clamp only runs when the buyer edits the quantity.
26 | Open risk: The order is charged at the server's current price, but the price can change between cart refresh and Place order; nothing says the buyer is told or asked to confirm, so the saved total can differ from the total on screen (payments risk).
27 | Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
28 | Split before the build: EST-2, EST-5, EST-8, EST-19 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).
S.No | Risks
1 | Estimates will increase in case of change in requirement
2 | EST-1 Data model: orders, order lines, order number sequence, parts indexes and seed data: the estimators disagree, so its range is wide
3 | EST-3 GET /api/parts: search, filters, paging, stock state: the estimators disagree, so its range is wide
4 | EST-4 GET /api/parts/brands: brand list from parts data: the estimators disagree, so its range is wide
5 | EST-5 Orders API: create with validation, list, detail, scoped to the buyer: the estimators disagree, so its range is wide
6 | EST-6 Order rules: pricing, totals, numbering, stock check, cancel state machine: the estimators disagree, so its range is wide
7 | EST-19 Environments, CI/CD and monitoring: the estimators disagree, so its range is wide

## Dev Mobile Estimates
Development Estimates for Parts Quick Order
2026-10-05
by mhamza
Not in scope: no work in this estimate
| Grand Total (in hours) | 0 | 0 | Sum of development, other activities and research efforts.
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
| None | 0 | 0
| Development Total Efforts (in hours) | 0 | 0
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | None | 0 | 0 | No research task in this estimate
| Research Total Efforts (in hours) | 0 | 0

## Dev Web Estimates
Development Estimates for Parts Quick Order
2026-10-05
by mhamza
| Grand Total (in hours) | 4.68 | 9.36 | Sum of development, other activities and research efforts.
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | Portal shell, sign-in wiring, navigation, accessibility and responsive layout | 4.68 | 9.36 |  |  |  |  | 10.44 | 19.44
| Web app shell: routes, header with links and cart count, layout, session wiring | 0 | 0 | routes /parts, /cart, /orders (exactly three screens); header links to the other two screens on each screen; header cart count = total of all quantities, updated live without reload; company login session wiring and buyer ID; responsive layout with no horizontal scroll at 360, 768, 1280 px; visible focus styles and keyboard navigation; shared GBP formatter (£ with 2 decimals), English-only copy; shared toast and inline alert components; error page / unknown route (One layout, 3 menu links, no roles in the menu, light theme only, English only: small. Accessibility and responsive layout are the cross-cutting UI factors [ui-shell web 8-14 h, small x0.6, context partial x1.2]) | Factory | REQ-1, REQ-9, REQ-36, REQ-37 | EST-7 | 5.76 | 10.08
| Production release | 4.68 | 9.36 | Production launch; delivers no requirement directly (One web target with a checklist (migrations, deploy, smoke test): typical [ops-release web 3-6 h, verify hard x1.3, context partial x1.2]) | Joint |  | EST-20 | 4.68 | 9.36
2 | Find parts (search, filters, paging, stock state, add to cart) | 0 | 0 |  |  |  |  | 6 | 10
| Find parts screen (S-1) | 0 | 0 | search box by name or part number with hint "Type at least 2 characters…"; Category and Brand filters, one each with All; brands loaded from /api/parts/brands; result rows: image, name, part no., brand, £ price, stock badge in text; Previous/Next page with "page x of y" and count; back to page 1 when search or filter changes; Add to cart button, disabled for out-of-stock parts; header count bumps after add; Go to cart (n) link; states: loading skeleton rows, empty "No parts match" with Clear search and filters button, error with Try again, low stock badge, added confirmation; first page shown within 2 s with 5,000 parts (Search plus 2 filters (category, brand), with paging and an add-to-cart row action. No bulk actions or inline edit: typical [ui-list web 6-10 h, typical]) | Factory | REQ-2, REQ-3, REQ-4, REQ-5, REQ-6, REQ-7, REQ-8, REQ-9, REQ-10, REQ-38 | EST-9 | 6 | 10
3 | Cart (lines, quantities, local storage, live price and stock refresh) | 0 | 0 |  |  |  |  | 25.48 | 40.04
| Cart and checkout screen (S-2), part 1: cart lines and CartStore | 0 | 0 | CartStore kept in local storage under the signed-in buyer's ID; addPart: add a line with quantity 1 or add 1 to it; nothing for out-of-stock parts; capped at stock with "Only n available"; cart table: part, part no., unit price, editable quantity, line total, Remove; line total = unit price × quantity; line and order totals recalculated at once; quantity correction: blank/0 → 1, above 99 → 99, decimals rounded; quantity above stock set to stock with "Only n available" next to the line; removeLine and count(); refresh on open: fetch current prices and stock from the parts API; use only current prices; line with 0 stock removed with "<part name> is now out of stock" alert; price fetch failure: lines without prices or totals, error message, Try again, checkout hidden; applyStockLimits for a 409: lower lines to available stock, remove lines with 0 available, keep other lines; states: loading prices, empty "Your cart is empty" with link to Find parts and checkout hidden; unit tests for CartStore acceptance criteria (One interactive widget (editable cart table with local storage) with 3 actions (edit quantity, remove, try again) plus refresh-on-open rules. No second widget and no real-time updates: typical [ui-complex web 14-22 h, rules-or-algorithm x1.3, complex UI x1.4]) | Factory | REQ-8, REQ-10, REQ-11, REQ-12, REQ-13, REQ-14, REQ-15, REQ-16, REQ-17, REQ-39, REQ-41, REQ-42, REQ-43 | EST-8 | 25.48 | 40.04
4 | Checkout and placing an order | 0 | 0 |  |  |  |  | 5.04 | 8.4
| Cart and checkout screen (S-2), part 2: checkout form and placing the order | 0 | 0 | Delivery address textarea, 5–200 characters, empty each time, with label and error "Enter a delivery address of 5 to 200 characters"; Delivery option radio Standard · £0.00 / Next day · £9.99 with error "Choose Standard or Next day"; Order summary: items, subtotal, delivery charge, total; CheckoutForm.canPlaceOrder: Place order enabled only with a valid address and an option chosen; startSubmit/finishSubmit: Place order disabled while the request runs; exactly one POST; success: show the new order number, empty the cart, link to My orders; 409 conflict: apply stock limits to the cart and show messages; network error toast "Connection lost. Check My orders before you try again."; cart, address and option kept; server error toast "Order not placed: server error. Your cart and details are kept."; unit tests for CheckoutForm (2 fields (address, delivery option) with validation, a summary block and submit handling. Up to 5 fields: small (the complex ui level carries the states) [ui-form web 6-10 h, small x0.6, complex UI x1.4]) | Factory | REQ-18, REQ-19, REQ-20, REQ-21, REQ-22, REQ-23, REQ-24, REQ-39, REQ-40 | EST-10 | 5.04 | 8.4
5 | My orders (list, status filter, detail panel, timeline, cancel) | 0 | 0 |  |  |  |  | 15.4 | 25.2
| My orders screen (S-3), part 1: orders table with status filter | 0 | 0 | table: order, placed date, items, total, status (text), newest first; status filter chips: All statuses, Placed, Packed, Dispatched, Delivered, Cancelled; View order opens the detail panel on the same /orders page (Enter key); states: loading skeleton rows, empty "No orders yet" with link to Find parts, filtered empty, error with Try again (Orders table with 1 status filter and empty, error and loading states. It has a filter, so it is more than a plain list, but there are not 4+ filters: typical [ui-list web 6-10 h, complex UI x1.4]) | Factory | REQ-1, REQ-28, REQ-29, REQ-35 | EST-11 | 8.4 | 14
| My orders screen (S-3), part 2: order detail drawer, timeline and cancel | 0 | 0 | drawer overlay: order number, date placed, lines (part number, name, qty, unit price, amount), delivery address, delivery option, total, status; timeline Placed → Packed → Dispatched → Delivered with the current step marked by text as well as colour; Cancel order button only while Placed; confirm dialog "Cancel ORD-…?" with Yes, cancel order / Keep order; no request sent when kept; success toast; status becomes Cancelled and the button is hidden; 409 refusal toast "Couldn't cancel: … has already been packed.", panel refreshes; focus handling for drawer and dialog by keyboard (Detail drawer with sections (lines, address, timeline) and 1-2 actions (cancel with confirm). No tabs or live widgets: typical [ui-detail web 5-8 h, complex UI x1.4]) | Factory | REQ-1, REQ-30, REQ-31, REQ-32, REQ-33, REQ-34 | EST-12 | 7 | 11.2
| Development Total Efforts (in hours) | 4.68 | 9.36
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | None | 0 | 0 | No research task in this estimate
| Research Total Efforts (in hours) | 0 | 0
S.No | Assumptions & Constraints
1 | Does the 'Place order' button also need the cart to have at least one line, or is that already covered because checkout is hidden when the cart is empty? → assumed: Covered already: checkout is hidden when the cart is empty, and the API also refuses an order with no lines
2 | Does placing (or cancelling) an order change the stock quantity in the existing parts database? → assumed: No: stock is read-only and orders never change it
3 | What happens when a cart quantity is more than the current stock (or the part is now out of stock) at the moment the buyer presses 'Place order'? → assumed: The API checks stock again, rejects the order, lowers the affected lines to the stock now available with 'Only n available', and keeps the cart
4 | Where is the cart kept? → assumed: In the browser's local storage for the signed-in buyer (kept across page reloads on the same device)
5 | How does the API find out which buyer is making a request through the existing company login? → assumed: The API checks the existing company login's session token or cookie and reads the buyer ID from it
6 | Nothing in this work moves an order to Packed, Dispatched or Delivered (no admin screens, no integrations). How do statuses change after Placed? → assumed: Staff update the status directly in the database, outside this work; the portal only shows it
7 | Which unit price is saved on an order line, and what does the order 'total' include? → assumed: The part's current price when the order is placed; total = subtotal + delivery charge
8 | How are 'ORD-' + 6-digit order numbers generated? → assumed: Sequential from a database sequence, zero-padded (ORD-000001)
9 | Should the delivery prices (£0 / £9.99), the stock thresholds (5) and the page size (20) be fixed in the code or set in configuration? → assumed: Fixed constants in the code
10 | What happens if the order's status changes from Placed (e.g. to Packed) after the buyer opened it but before they confirm cancelling? → assumed: The API cancels only if the status is still Placed; otherwise it refuses, shows a message and refreshes the order
11 | What happens if placing an order fails (network or server error)? → assumed: Show an error message, keep the cart and checkout details, and let the buyer try again
12 | What happens when a quantity is set to 0, left blank, set above 99, or isn't a whole number? → assumed: Set it to the nearest value in range (blank or 0 becomes 1, above 99 becomes 99)
13 | What do 'cart count' in the header and 'number of items' in My orders count? → assumed: The total of all quantities (2 filters + 1 pad = 3)
14 | How do the parts list filters and sort order work? → assumed: One category and one brand at a time (each with 'All'), brands taken from the parts data, sorted by name A–Z, back to page 1 whenever the search or a filter changes
15 | Is the delivery address remembered from the buyer's previous order? → assumed: No: typed fresh for each order
16 | Under what conditions is the 2-second load target measured, and how many buyers and orders are expected? → assumed: Up to 1,000 users and 100,000 records in the first year.
17 | Which browsers must be supported? → assumed: The latest two versions of Chrome, Edge, Safari and Firefox.
18 | Are orders written to the same PostgreSQL database that holds the existing parts? → assumed: Yes: new orders and order-lines tables in the same database, referring to parts by part number
19 | Spec question Q-1: If a part in the cart now has 0 stock, what should happen to that cart line? (One rule says the quantity can never go below 1. Another says it can never go above stock.) → Remove the line and show "<part name> is now out of stock" (assumed by the factory, hands-off)
20 | Spec question Q-2: If the buyer retries after a network error but the first order was actually saved, how should we stop the order being placed twice? → Disable "Place order" while a request is in progress, and on a network error tell the buyer to check My orders before retrying (assumed by the factory, hands-off)
21 | Spec question Q-3: The cart keeps a saved copy of each price, but orders are charged at the current price. How should the cart handle a price that has changed? → Fetch the current prices from the parts API when the cart opens, and show only those (assumed by the factory, hands-off)
22 | Spec question Q-4: Should the spec keep a separate requirement that the API rejects requests with no valid company-login session (status 401)? The request doesn't mention this. → Leave it out and rely on the existing company login as-is (assumed by the factory, hands-off)
23 | Spec question Q-5: When the cart opens and the request to the parts API for current prices fails (network or server error), what should the cart show and allow? The saved prices must never be shown. → Show the cart lines without prices or totals, show an error message with a "Try again" button, and hide checkout until current prices load (assumed by the factory, hands-off)
24 | Open risk: ASM-26 and AC-41.1 need GET /api/parts filtered to the cart's part numbers in a single call, but REQ-2/4/5 and ASM-19 only define q (at least 2 characters, substring match), category, brand and page, so no defined parameter can fetch exactly the cart's parts.
25 | Open risk: When the cart opens, only lines whose part now has 0 stock are handled; a line whose stock has dropped but is still above 0 (cart quantity 5, stock now 2) is left unclamped until the 409 at Place order, and REQ-14's clamp only runs when the buyer edits the quantity.
26 | Open risk: The order is charged at the server's current price, but the price can change between cart refresh and Place order; nothing says the buyer is told or asked to confirm, so the saved total can differ from the total on screen (payments risk).
27 | Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
28 | Split before the build: EST-2, EST-5, EST-8, EST-19 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).
S.No | Risks
1 | Estimates will increase in case of change in requirement

## QA Estimates
QA Estimates for Parts Quick Order
2026-10-05
by mhamza
| Grand Total Efforts (in hours) | 4 | 8 | Sum of QA and Misc.
S.No | Estimation Summary | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | Test Plan/Strategy | 0 | 0 | Test planning, with the test plan, strategy and traceability matrix as outputs. Not sized in this estimate
2 | Set up of Test Environments | 0 | 0 | Setting up code and white box test environments. Not sized in this estimate
3 | Validation and Smoke test cases | 0 | 0 | Test cases to execute while debugging and white box testing |  |  |  | 12.9 | 25.8
| Test cases: Find parts, including performance | 0 | 0 | API cases AC-2.x, AC-3.x, AC-4.x, AC-5.x, AC-7.1; manual cases AC-6.1, AC-7.2, AC-9.2, AC-10.2; AC-38.1 p95 under 500 ms with 5,000 parts; AC-38.2 first page within 2 s; NFR-1 load check at 1,000 concurrent users (4 flows (search and filter, paging, add to cart and stock state, performance and load) for one role: typical [qa-cases qa 3-6 h, verify hard x1.3]) | Factory | REQ-2, REQ-3, REQ-4, REQ-5, REQ-6, REQ-7, REQ-8, REQ-9, REQ-10, REQ-38 | EST-14 | 3.9 | 7.8
| Test cases: Cart | 0 | 0 | manual cases AC-12.2, AC-14.2, AC-17.1, AC-41.2, AC-43.4, AC-43.5; check that unit cases for CartStore are covered (3 flows (quantity edit and limits, persistence and empty cart, price refresh and failure): typical [qa-cases qa 3-6 h, typical]) | Factory | REQ-11, REQ-12, REQ-13, REQ-14, REQ-15, REQ-16, REQ-17, REQ-39, REQ-41, REQ-42, REQ-43 | EST-15 | 3 | 6
| Test cases: Checkout and placing orders | 0 | 0 | API cases AC-20.x, AC-21.x, AC-22.1, AC-25.1; manual cases AC-18.3, AC-23.1, AC-24.1, AC-24.2, AC-40.3 (4 flows (validation, successful placement, 409 stock conflict, network and server errors): typical [qa-cases qa 3-6 h, typical]) | Factory | REQ-18, REQ-19, REQ-20, REQ-21, REQ-22, REQ-23, REQ-24, REQ-25, REQ-40 | EST-16 | 3 | 6
| Test cases: My orders | 0 | 0 | API cases AC-27.x, AC-28.1, AC-29.1, AC-30.1, AC-33.1, AC-34.1, AC-35.1; manual cases AC-31.1, AC-32.1, AC-32.2, AC-34.2, AC-35.2 (4 flows (list and status filter, empty state, detail and timeline, cancel and refusal): typical [qa-cases qa 3-6 h, typical]) | Factory | REQ-27, REQ-28, REQ-29, REQ-30, REQ-31, REQ-32, REQ-33, REQ-34, REQ-35 | EST-17 | 3 | 6
4 | Validation testing | 0 | 0 | Testing cycles; the detail is below
| Testing Cycle 1 | 0 | 0
5 | Smoke testing | 0 | 0 | Smoke testing after each deployment, including preparation. Not sized in this estimate
6 | Multi Browser Compatibility testing | 0 | 0 | Browser, OS and device compatibility |  |  |  | 3.9 | 7.8
| Test cases: navigation, accessibility, responsive layout, browsers | 0 | 0 | AC-1.1, AC-1.2; AC-36.1 at 360/768/1280 px on the latest 2 versions of Chrome, Edge, Safari, Firefox; AC-37.1 keyboard-only run with a screen reader; axe scan of each screen: 0 serious or critical violations; stock and status indicators carry text (3 flows (navigation, responsive layout across browsers, keyboard and screen-reader accessibility) for one role: typical [qa-cases qa 3-6 h, verify hard x1.3]) | Factory | REQ-1, REQ-36, REQ-37 | EST-13 | 3.9 | 7.8
7 | UAT | 4 | 8 | Client user acceptance testing support |  |  |  | 4 | 8
| Client acceptance testing | 4 | 8 | Client UAT of the finished portal; delivers no requirement directly (One UAT round with one round of feedback fixes: typical [qa-uat qa 4-8 h, typical]) | Human |  | EST-21 | 4 | 8
8 | Misc. Optional testing | 0 | 0 | Other testing named in the breakdown, and supervisor gate time. Not sized in this estimate
| Total QA Efforts | 4 | 8 | Total hours of QA
S.No | Validation Testing | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
Testing Cycle 1
1 | Automated end-to-end test: search to order to cancel | 0 | 0 | search and filter, add to cart, header count updates; change quantity, enter address, choose delivery, place order, order number shown, cart emptied; open the order in My orders, cancel with confirmation, status Cancelled (3 chained flows (find and add to cart, checkout and place order, open and cancel the order) on one platform: large [qa-e2e qa 6-10 h, large x1.6]) | Factory | REQ-4, REQ-5, REQ-8, REQ-9, REQ-18, REQ-20, REQ-23, REQ-28, REQ-30, REQ-32, REQ-33 | EST-18 | 9.6 | 16
| Total Testing Cycle 1 | 0 | 0 | Sum of testing cycle 1
S.No | Assumptions & Constraints
1 | Does the 'Place order' button also need the cart to have at least one line, or is that already covered because checkout is hidden when the cart is empty? → assumed: Covered already: checkout is hidden when the cart is empty, and the API also refuses an order with no lines
2 | Does placing (or cancelling) an order change the stock quantity in the existing parts database? → assumed: No: stock is read-only and orders never change it
3 | What happens when a cart quantity is more than the current stock (or the part is now out of stock) at the moment the buyer presses 'Place order'? → assumed: The API checks stock again, rejects the order, lowers the affected lines to the stock now available with 'Only n available', and keeps the cart
4 | Where is the cart kept? → assumed: In the browser's local storage for the signed-in buyer (kept across page reloads on the same device)
5 | How does the API find out which buyer is making a request through the existing company login? → assumed: The API checks the existing company login's session token or cookie and reads the buyer ID from it
6 | Nothing in this work moves an order to Packed, Dispatched or Delivered (no admin screens, no integrations). How do statuses change after Placed? → assumed: Staff update the status directly in the database, outside this work; the portal only shows it
7 | Which unit price is saved on an order line, and what does the order 'total' include? → assumed: The part's current price when the order is placed; total = subtotal + delivery charge
8 | How are 'ORD-' + 6-digit order numbers generated? → assumed: Sequential from a database sequence, zero-padded (ORD-000001)
9 | Should the delivery prices (£0 / £9.99), the stock thresholds (5) and the page size (20) be fixed in the code or set in configuration? → assumed: Fixed constants in the code
10 | What happens if the order's status changes from Placed (e.g. to Packed) after the buyer opened it but before they confirm cancelling? → assumed: The API cancels only if the status is still Placed; otherwise it refuses, shows a message and refreshes the order
11 | What happens if placing an order fails (network or server error)? → assumed: Show an error message, keep the cart and checkout details, and let the buyer try again
12 | What happens when a quantity is set to 0, left blank, set above 99, or isn't a whole number? → assumed: Set it to the nearest value in range (blank or 0 becomes 1, above 99 becomes 99)
13 | What do 'cart count' in the header and 'number of items' in My orders count? → assumed: The total of all quantities (2 filters + 1 pad = 3)
14 | How do the parts list filters and sort order work? → assumed: One category and one brand at a time (each with 'All'), brands taken from the parts data, sorted by name A–Z, back to page 1 whenever the search or a filter changes
15 | Is the delivery address remembered from the buyer's previous order? → assumed: No: typed fresh for each order
16 | Under what conditions is the 2-second load target measured, and how many buyers and orders are expected? → assumed: Up to 1,000 users and 100,000 records in the first year.
17 | Which browsers must be supported? → assumed: The latest two versions of Chrome, Edge, Safari and Firefox.
18 | Are orders written to the same PostgreSQL database that holds the existing parts? → assumed: Yes: new orders and order-lines tables in the same database, referring to parts by part number
19 | Spec question Q-1: If a part in the cart now has 0 stock, what should happen to that cart line? (One rule says the quantity can never go below 1. Another says it can never go above stock.) → Remove the line and show "<part name> is now out of stock" (assumed by the factory, hands-off)
20 | Spec question Q-2: If the buyer retries after a network error but the first order was actually saved, how should we stop the order being placed twice? → Disable "Place order" while a request is in progress, and on a network error tell the buyer to check My orders before retrying (assumed by the factory, hands-off)
21 | Spec question Q-3: The cart keeps a saved copy of each price, but orders are charged at the current price. How should the cart handle a price that has changed? → Fetch the current prices from the parts API when the cart opens, and show only those (assumed by the factory, hands-off)
22 | Spec question Q-4: Should the spec keep a separate requirement that the API rejects requests with no valid company-login session (status 401)? The request doesn't mention this. → Leave it out and rely on the existing company login as-is (assumed by the factory, hands-off)
23 | Spec question Q-5: When the cart opens and the request to the parts API for current prices fails (network or server error), what should the cart show and allow? The saved prices must never be shown. → Show the cart lines without prices or totals, show an error message with a "Try again" button, and hide checkout until current prices load (assumed by the factory, hands-off)
24 | Open risk: ASM-26 and AC-41.1 need GET /api/parts filtered to the cart's part numbers in a single call, but REQ-2/4/5 and ASM-19 only define q (at least 2 characters, substring match), category, brand and page, so no defined parameter can fetch exactly the cart's parts.
25 | Open risk: When the cart opens, only lines whose part now has 0 stock are handled; a line whose stock has dropped but is still above 0 (cart quantity 5, stock now 2) is left unclamped until the 409 at Place order, and REQ-14's clamp only runs when the buyer edits the quantity.
26 | Open risk: The order is charged at the server's current price, but the price can change between cart refresh and Place order; nothing says the buyer is told or asked to confirm, so the saved total can differ from the total on screen (payments risk).
27 | Gate time, cost and duration are assumed figures, labelled cold-start until the ledger has measured runs.
28 | Split before the build: EST-2, EST-5, EST-8, EST-19 (agent work over 16 h or very large is split into smaller tasks; the hours stay as estimated).
S.No | Risks
1 | Estimates will increase in case of change in requirement
2 | EST-13 Test cases: navigation, accessibility, responsive layout, browsers: the estimators disagree, so its range is wide
3 | EST-14 Test cases: Find parts, including performance: the estimators disagree, so its range is wide
4 | EST-18 Automated end-to-end test: search to order to cancel: the estimators disagree, so its range is wide

## Design Estimates
Design Estimates for Parts Quick Order
2026-10-05
by mhamza
Not in scope: no work in this estimate
| Grand Total (in hours) | 0 | 0 | Sum of development, other activities and research efforts.
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
| None | 0 | 0
| Development Total Efforts (in hours) | 0 | 0
S.No | Other Development Activities | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| Post Development Activities Total Efforts (in hours) | 0 | 0
S.No | Research Task (if any) | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | None | 0 | 0 | No research task in this estimate
| Research Total Efforts (in hours) | 0 | 0

## Other Estimates
Other Estimates for Parts Quick Order
2026-10-05
by mhamza
GD
Not in scope: no work in this estimate
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| GD TOTAL | 0 | 0
PM
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | Project management | 16 | 24 | Project management across the build; delivers no requirement directly (3 screens and a small API, about a month of delivery: typical [pm-management pm 16-24 h, typical]) | Human |  | EST-22 | 16 | 24
| PM TOTAL | 16 | 24
PDM
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | Handover notes | 0 | 0 | Documentation for the client's team; delivers no requirement directly (Short handover notes on 3 topics (status updates, constants, login dependency), roughly a one-page guide: small [pdm-docs pdm 4-8 h, small x0.6]) | Factory |  | EST-23 | 2.4 | 4.8
| PDM TOTAL | 0 | 0
Cross-cutting
S.No | Task | Minimum | Maximum | Comments | Executor | Requirement id(s) | Task id | Sized min (h) | Sized max (h)
1 | None | 0 | 0 |  |  |  |  | 0 | 0
| Cross-cutting TOTAL | 0 | 0

## Confidence
Delivery model | agentic
Size band | M
Uncertainty | medium
Cost confidence | cold-start
Benchmark records | 6
Flagged tasks (estimators disagree) | 9
Spec sha | 78b80754217423dd7f9683d91dfad757f88541fda28cac9620b2e3c8747d658c
Breakdown sha | df31346a9cd673ce95341eead79a2797f3a6a9e7aabeb856bc09ff0259047959
Task catalogue | 2026-10-03.1 (stack dotnet)
Catalogue status | reference hours, not yet measured

## Anchors
Anchors
Task | Title | Min (h) | Max (h) | Why a fair reference
EST-1 | Data model: orders, order lines, order number sequence, parts indexes and seed data | 2.59 | 5.18 | 2 new tables (orders, order_lines) plus a sequence, with indexes and a parts seed on an existing table. That is up to 3 entities and no existing data is migrated: small [be-data backend 4-8 h, small x0.6, verify easy x0.9, context partial x1.2]
EST-2 | Buyer identity from the existing company login session | 13.1 | 20.97 | One sign-in method (reusing the existing company session) and one buyer role: small [be-auth backend 10-16 h, small x0.6, external-dependency x1.4, verify hard x1.3, context partial x1.2]
EST-3 | GET /api/parts: search, filters, paging, stock state | 3 | 6 | Search plus 2 filters (category, brand), paging, sorting and a derived stock state, with no joins over 3+ tables or aggregates: typical [be-endpoint backend 3-6 h, typical]
EST-5 | Orders API: create with validation, list, detail, scoped to the buyer | 11.52 | 17.28 | Order of about 7 fields with order lines and a part reference (2 relations), but it also needs custom queries (status filter, itemCount sum, buyer scoping, lookup by order number) and 6 validation rules: large [be-crud backend 8-12 h, large x1.6, verify easy x0.9]
EST-6 | Order rules: pricing, totals, numbering, stock check, cancel state machine | 8 | 14 | 8 rules (price snapshot, total and delivery charge, numbering, transactional stock check, stock untouched, conditional cancel, 409, 404) and only a Placed to Cancelled transition: typical [be-rules backend 8-14 h, typical]
EST-7 | Web app shell: routes, header with links and cart count, layout, session wiring | 5.76 | 10.08 | One layout, 3 menu links, no roles in the menu, light theme only, English only: small. Accessibility and responsive layout are the cross-cutting UI factors [ui-shell web 8-14 h, small x0.6, context partial x1.2]
EST-8 | Cart and checkout screen (S-2), part 1: cart lines and CartStore | 25.48 | 40.04 | One interactive widget (editable cart table with local storage) with 3 actions (edit quantity, remove, try again) plus refresh-on-open rules. No second widget and no real-time updates: typical [ui-complex web 14-22 h, rules-or-algorithm x1.3, complex UI x1.4]
EST-9 | Find parts screen (S-1) | 6 | 10 | Search plus 2 filters (category, brand), with paging and an add-to-cart row action. No bulk actions or inline edit: typical [ui-list web 6-10 h, typical]
EST-10 | Cart and checkout screen (S-2), part 2: checkout form and placing the order | 5.04 | 8.4 | 2 fields (address, delivery option) with validation, a summary block and submit handling. Up to 5 fields: small (the complex ui level carries the states) [ui-form web 6-10 h, small x0.6, complex UI x1.4]
EST-12 | My orders screen (S-3), part 2: order detail drawer, timeline and cancel | 7 | 11.2 | Detail drawer with sections (lines, address, timeline) and 1-2 actions (cancel with confirm). No tabs or live widgets: typical [ui-detail web 5-8 h, complex UI x1.4]
EST-13 | Test cases: navigation, accessibility, responsive layout, browsers | 3.9 | 7.8 | 3 flows (navigation, responsive layout across browsers, keyboard and screen-reader accessibility) for one role: typical [qa-cases qa 3-6 h, verify hard x1.3]
EST-18 | Automated end-to-end test: search to order to cancel | 9.6 | 16 | 3 chained flows (find and add to cart, checkout and place order, open and cancel the order) on one platform: large [qa-e2e qa 6-10 h, large x1.6]
EST-19 | Environments, CI/CD and monitoring | 12.48 | 21.84 | Dev, staging and production with a CI pipeline and monitoring, but no infrastructure as code is asked for. That falls between typical and large, so the smaller step: typical [ops-setup backend 8-14 h, verify hard x1.3, context partial x1.2]
EST-20 | Production release | 4.68 | 9.36 | One web target with a checklist (migrations, deploy, smoke test): typical [ops-release web 3-6 h, verify hard x1.3, context partial x1.2]
EST-21 | Client acceptance testing | 4 | 8 | One UAT round with one round of feedback fixes: typical [qa-uat qa 4-8 h, typical]
EST-22 | Project management | 16 | 24 | 3 screens and a small API, about a month of delivery: typical [pm-management pm 16-24 h, typical]
EST-23 | Handover notes | 2.4 | 4.8 | Short handover notes on 3 topics (status updates, constants, login dependency), roughly a one-page guide: small [pdm-docs pdm 4-8 h, small x0.6]
Task | Title | Anchor | Ratio | Reason | Min (h) | Max (h) | Executor | Flagged
EST-1 | Data model: orders, order lines, order number sequence, parts indexes and seed data | EST-1 | 1 | 2 new tables (orders, order_lines) plus a sequence, with indexes and a parts seed on an existing table. That is up to 3 entities and no existing data is migrated: small [be-data backend 4-8 h, small x0.6, verify easy x0.9, context partial x1.2] | 2.59 | 5.18 | factory | yes
EST-2 | Buyer identity from the existing company login session | EST-2 | 1 | One sign-in method (reusing the existing company session) and one buyer role: small [be-auth backend 10-16 h, small x0.6, external-dependency x1.4, verify hard x1.3, context partial x1.2] | 13.1 | 20.97 | joint
EST-3 | GET /api/parts: search, filters, paging, stock state | EST-3 | 1 | Search plus 2 filters (category, brand), paging, sorting and a derived stock state, with no joins over 3+ tables or aggregates: typical [be-endpoint backend 3-6 h, typical] | 3 | 6 | factory | yes
EST-4 | GET /api/parts/brands: brand list from parts data | EST-3 | 0.54 | One plain distinct read of brands, with no filters or paging: small [be-endpoint backend 3-6 h, small x0.6, verify easy x0.9] | 1.62 | 3.24 | factory | yes
EST-5 | Orders API: create with validation, list, detail, scoped to the buyer | EST-5 | 1 | Order of about 7 fields with order lines and a part reference (2 relations), but it also needs custom queries (status filter, itemCount sum, buyer scoping, lookup by order number) and 6 validation rules: large [be-crud backend 8-12 h, large x1.6, verify easy x0.9] | 11.52 | 17.28 | factory | yes
EST-6 | Order rules: pricing, totals, numbering, stock check, cancel state machine | EST-6 | 1 | 8 rules (price snapshot, total and delivery charge, numbering, transactional stock check, stock untouched, conditional cancel, 409, 404) and only a Placed to Cancelled transition: typical [be-rules backend 8-14 h, typical] | 7.2 | 12.6 | factory | yes
EST-7 | Web app shell: routes, header with links and cart count, layout, session wiring | EST-7 | 1 | One layout, 3 menu links, no roles in the menu, light theme only, English only: small. Accessibility and responsive layout are the cross-cutting UI factors [ui-shell web 8-14 h, small x0.6, context partial x1.2] | 5.76 | 10.08 | factory
EST-8 | Cart and checkout screen (S-2), part 1: cart lines and CartStore | EST-8 | 1 | One interactive widget (editable cart table with local storage) with 3 actions (edit quantity, remove, try again) plus refresh-on-open rules. No second widget and no real-time updates: typical [ui-complex web 14-22 h, rules-or-algorithm x1.3, complex UI x1.4] | 25.48 | 40.04 | factory
EST-9 | Find parts screen (S-1) | EST-9 | 1 | Search plus 2 filters (category, brand), with paging and an add-to-cart row action. No bulk actions or inline edit: typical [ui-list web 6-10 h, typical] | 6 | 10 | factory
EST-10 | Cart and checkout screen (S-2), part 2: checkout form and placing the order | EST-10 | 1 | 2 fields (address, delivery option) with validation, a summary block and submit handling. Up to 5 fields: small (the complex ui level carries the states) [ui-form web 6-10 h, small x0.6, complex UI x1.4] | 5.04 | 8.4 | factory
EST-11 | My orders screen (S-3), part 1: orders table with status filter | EST-9 | 1.4 | Orders table with 1 status filter and empty, error and loading states. It has a filter, so it is more than a plain list, but there are not 4+ filters: typical [ui-list web 6-10 h, complex UI x1.4] | 8.4 | 14 | factory
EST-12 | My orders screen (S-3), part 2: order detail drawer, timeline and cancel | EST-12 | 1 | Detail drawer with sections (lines, address, timeline) and 1-2 actions (cancel with confirm). No tabs or live widgets: typical [ui-detail web 5-8 h, complex UI x1.4] | 7 | 11.2 | factory
EST-13 | Test cases: navigation, accessibility, responsive layout, browsers | EST-13 | 1 | 3 flows (navigation, responsive layout across browsers, keyboard and screen-reader accessibility) for one role: typical [qa-cases qa 3-6 h, verify hard x1.3] | 3.9 | 7.8 | factory | yes
EST-14 | Test cases: Find parts, including performance | EST-13 | 1 | 4 flows (search and filter, paging, add to cart and stock state, performance and load) for one role: typical [qa-cases qa 3-6 h, verify hard x1.3] | 3.9 | 7.8 | factory | yes
EST-15 | Test cases: Cart | EST-13 | 0.769 | 3 flows (quantity edit and limits, persistence and empty cart, price refresh and failure): typical [qa-cases qa 3-6 h, typical] | 3 | 6 | factory
EST-16 | Test cases: Checkout and placing orders | EST-13 | 0.769 | 4 flows (validation, successful placement, 409 stock conflict, network and server errors): typical [qa-cases qa 3-6 h, typical] | 3 | 6 | factory
EST-17 | Test cases: My orders | EST-13 | 0.769 | 4 flows (list and status filter, empty state, detail and timeline, cancel and refusal): typical [qa-cases qa 3-6 h, typical] | 3 | 6 | factory
EST-18 | Automated end-to-end test: search to order to cancel | EST-18 | 1 | 3 chained flows (find and add to cart, checkout and place order, open and cancel the order) on one platform: large [qa-e2e qa 6-10 h, large x1.6] | 9.6 | 16 | factory | yes
EST-19 | Environments, CI/CD and monitoring | EST-19 | 1 | Dev, staging and production with a CI pipeline and monitoring, but no infrastructure as code is asked for. That falls between typical and large, so the smaller step: typical [ops-setup backend 8-14 h, verify hard x1.3, context partial x1.2] | 12.48 | 21.84 | joint | yes
EST-20 | Production release | EST-20 | 1 | One web target with a checklist (migrations, deploy, smoke test): typical [ops-release web 3-6 h, verify hard x1.3, context partial x1.2] | 4.68 | 9.36 | joint
EST-21 | Client acceptance testing | EST-21 | 1 | One UAT round with one round of feedback fixes: typical [qa-uat qa 4-8 h, typical] | 4 | 8 | human
EST-22 | Project management | EST-22 | 1 | 3 screens and a small API, about a month of delivery: typical [pm-management pm 16-24 h, typical] | 16 | 24 | human
EST-23 | Handover notes | EST-23 | 1 | Short handover notes on 3 topics (status updates, constants, login dependency), roughly a one-page guide: small [pdm-docs pdm 4-8 h, small x0.6] | 2.4 | 4.8 | factory

## Traceability
Requirements and traceability
Requirement | Title | Tasks
REQ-1 | The portal shall provide exactly three screens for the signed-in buyer: Find parts at /parts, Cart and checkout at /cart, and My orders a... | EST-7, EST-11, EST-12, EST-13
REQ-10 | If a part is out of stock, then the portal shall disable its "Add to cart" button. | EST-8, EST-9, EST-14
REQ-11 | The cart shall give each line its name, part number, unit price, quantity and line total, where line total = unit price × quantity. | EST-8, EST-15
REQ-12 | When the buyer changes a line quantity, the cart shall recalculate that line total and the order totals at once. | EST-8, EST-15
REQ-13 | If the buyer enters a quantity that is blank, 0, above 99 or not a whole number, then the cart shall set it to the nearest whole number f... | EST-8, EST-15
REQ-14 | If the buyer enters a quantity above the part's stock, then the cart shall set the quantity to the stock quantity and give the message "O... | EST-8, EST-15
REQ-15 | When the buyer presses "Remove" on a cart line, the cart shall remove that line. | EST-8, EST-15
REQ-16 | The cart shall keep its lines in the browser's local storage under the signed-in buyer's ID, so the cart survives page reloads on the sam... | EST-8, EST-15
REQ-17 | While the cart is empty, the portal shall show "Your cart is empty" with a link to Find parts and hide checkout. | EST-8, EST-15
REQ-18 | The checkout shall enable "Place order" only when the delivery address has 5 to 200 characters and a delivery option (Standard or Next da... | EST-10, EST-16, EST-18
REQ-19 | The checkout shall show subtotal, delivery charge (Standard £0.00, Next day £9.99) and total, where total = subtotal + delivery charge. | EST-10, EST-16
REQ-2 | When a buyer requests the parts list, the parts API shall return parts sorted by name A–Z, 20 per page, each with image (or none), name, ... | EST-3, EST-9, EST-14
REQ-20 | When the buyer places an order with valid lines, address and delivery option, the orders API shall save an order with status Placed, a se... | EST-1, EST-5, EST-6, EST-10, EST-16, EST-18
REQ-21 | If a place-order request has no lines, a quantity outside 1–99, an unknown part number, an address outside 5–200 characters, or a missing... | EST-5, EST-10, EST-16
REQ-22 | If any line's quantity is above the part's stock when an order is placed, then the orders API shall reject the order with status 409 and ... | EST-6, EST-10, EST-16
REQ-23 | When an order is placed successfully, the portal shall empty the cart and show the new order number. | EST-10, EST-16, EST-18
REQ-24 | If placing an order fails with a network error or a server error, then the portal shall show an error message, which for a network error ... | EST-10, EST-16
REQ-25 | The orders API shall leave the stock quantity in the parts database unchanged when an order is placed or cancelled. | EST-6, EST-16
REQ-27 | The orders API shall return to a buyer only the orders placed by that buyer. | EST-2, EST-5, EST-6, EST-17
REQ-28 | When a buyer requests their orders, the orders API shall return them newest first, each with order number, date placed, number of items (... | EST-1, EST-5, EST-11, EST-17, EST-18
REQ-29 | When the buyer picks a status filter on My orders, the orders API shall return only that buyer's orders with that status. | EST-5, EST-11, EST-17
REQ-3 | The parts API shall set a part's stock state to "In stock" when stock is 5 or more, "Low stock (n left)" when stock is 1 to 4, and "Out o... | EST-3, EST-9, EST-14
REQ-30 | When a buyer opens one of their orders, the orders API shall return its lines (part number, name, quantity, unit price), delivery address... | EST-5, EST-12, EST-17, EST-18
REQ-31 | When the buyer opens an order, the portal shall show a status timeline Placed → Packed → Dispatched → Delivered with the current status m... | EST-12, EST-17
REQ-32 | While an order's status is Placed, the portal shall show a "Cancel order" button in the order detail that asks for confirmation before ca... | EST-12, EST-17, EST-18
REQ-33 | When a buyer cancels their order whose status is still Placed, the orders API shall set the status to Cancelled. | EST-6, EST-12, EST-17, EST-18
REQ-34 | If the order's status is no longer Placed when the buyer confirms cancelling, then the orders API shall refuse with status 409 and leave ... | EST-6, EST-12, EST-17
REQ-35 | While the buyer has no orders, the portal shall show "No orders yet" and a link to Find parts on My orders. | EST-5, EST-11, EST-17
REQ-36 | The portal shall show all three screens without horizontal scrolling at viewport widths from 360 px upwards. | EST-7, EST-13
REQ-37 | The portal shall give every form field a visible text label and let the buyer reach and use every control by keyboard alone. | EST-7, EST-13
REQ-38 | While the parts database holds 5,000 parts, the Find parts screen shall load its first page of results in under 2 seconds. | EST-1, EST-3, EST-9, EST-14
REQ-39 | When the orders API rejects an order with a 409 stock conflict, the cart shall lower each affected line to the stock now available with t... | EST-8, EST-10, EST-15
REQ-4 | When the search text has at least 2 characters, the parts API shall return only parts whose name or part number contains that text, ignor... | EST-3, EST-9, EST-14, EST-18
REQ-40 | While a place-order request is in progress, the checkout shall disable "Place order". | EST-10, EST-16
REQ-41 | When the buyer opens the cart, the cart shall fetch the current price of each line's part from the parts API and use only those current p... | EST-8, EST-15
REQ-42 | If the current part data fetched when the cart opens shows a cart line's part has 0 stock, then the cart shall remove that line and give ... | EST-8, EST-15
REQ-43 | If the request to the parts API for current prices fails with a network or server error when the cart opens, then the cart shall show the... | EST-8, EST-15
REQ-5 | When the buyer picks a category or brand filter, the parts API shall return only parts matching that one category and that one brand, com... | EST-3, EST-4, EST-9, EST-14, EST-18
REQ-6 | When the search text or a filter changes on Find parts, the portal shall show page 1 of the results. | EST-9, EST-14
REQ-7 | When no part matches the search and filters, the portal shall show "No parts match" and a button that clears the search and filters. | EST-3, EST-9, EST-14
REQ-8 | When the buyer presses "Add to cart" on a part that is in stock, the cart shall add a line with quantity 1, or raise the existing line's ... | EST-8, EST-9, EST-14, EST-18
REQ-9 | The portal shall show in the header a cart count equal to the total of all quantities in the cart, updated whenever the cart changes. | EST-7, EST-9, EST-14, EST-18
Tasks with no requirement (named overheads)
EST-19 | Environments, CI/CD and monitoring | Environment and pipeline setup; delivers no requirement directly
EST-20 | Production release | Production launch; delivers no requirement directly
EST-21 | Client acceptance testing | Client UAT of the finished portal; delivers no requirement directly
EST-22 | Project management | Project management across the build; delivers no requirement directly
EST-23 | Handover notes | Documentation for the client's team; delivers no requirement directly

## Parameters
Assumed parameters and gate time (all editable, all assumed)
Parameter | Min | Max
Clarify minutes per question | 2 | 5
Approval minutes per section | 3 | 8
PR review minutes, low risk | 10 | 20
PR review minutes, medium risk | 20 | 40
PR review minutes, high risk | 40 | 90
Parked-run rate | 0.05 | 0.15
Parked-run intervention minutes | 20 | 60
Waiver minutes | 5 | 15
Cold-start dollars per task | 1.3 | 1.8
Estimator tolerance | 0.5
Tasks per PR | 2
Hours per day | 8
Hours per week | 40
Agentic build factor | 1.25
Gate hours in this estimate
None: the solely agentic model has no supervisor gates
No rates were given, so there is no cost overlay.

## Gates
Estimate gates and waivers
Gate | Result | Details
estimate.e1b-design-baseline | passed | 3 screens approved and linked to requirements
estimate.e1-readiness | passed | 42 requirements, lint, critic and round trip clean (8 problems settled by questions), no open questions
estimate.e2-req-to-task | passed | all 42 requirements have a task
estimate.e3-task-to-req | passed | every task cites a requirement or a named overhead
estimate.e2c-task-kind | passed | every task has a catalogue kind that fits its track (catalogue 2026-10-03.1)
estimate.e4-checklist | passed | 14 checklist items each in, or out with a reason
estimate.e1c-design-coverage | passed | all 3 approved screens are built by a task, and every task screen is approved
estimate.e5-consistency | passed | similar tasks are within tolerance
estimate.e6-lint | passed | totals, ratios and costs recompute cleanly
estimate.e7-approval | passed | approved by the factory (no human review)
Waivers
Gates | Step | Waived by and why
None